## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08815 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Part-I (Gobindapur) at Hanskhali Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000125/2021-2022 | 50/NAD-I | 11/01/2022 | 11/04/2022 | M/S DIPAK ENTERPRISE | 128.71 | 128.56 | 99.88 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08815 | Retrofitting | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for GOBINDAPUR ZONE-II Water Supply Scheme of Nadia District under Nadia Arsenic-I Division, PHE Dte. (Sl. No.-04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000411/2020-2021 | 61/AE-I/N.A.D.-I | 24/02/2021 | 26/03/2021 | UMWELT ENGINEER PVT. LTD. | 3.68 | 3.68 | 100 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08815 | Retrofitting | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for GOBINDAPUR ZONE-I Water Supply Scheme under Nadia Arsenic-I Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000410/2020-2021 | 59/AE-I/N.A.D.-I | 24/02/2021 | 26/03/2021 | UMWELT ENGINEER PVT. LTD. | 4.6 | 4.6 | 100 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08815 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Hanskhali BDO, BL&LRO, Ration Deptt, Animal Husbandary,Health etc, at Hanskhali Block by retrofitting of Ground Water based PWSS for Gobindapur (Hanskhali) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000134/2022-2023 | 266/AE-I/NAD-I | 09/11/2022 | 24/11/2022 | BUDDHADEV MONDAL | 4.66 | 4.66 | 99.99 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08815 | Retrofitting | Construction of Boundary wall, Land Development, Construction of Pathway & other allied works at Headwork site of Gobindapur (Hanskhali) under Hanskhali Dev. Block water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte. Length of Boundary wall - 145 mtr. metre. | Assistant Engineer-II | Junior Engineer-I | ORD/000130/2021-2022 | 74/NAD-I | 17/01/2022 | 16/02/2022 | NISHITH BANERJEE | 16.71 | 0 | 0 | 70
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08815 | Retrofitting | Balance work for revamping / upgradation of the hydraulic parameters at Kalipara,Gobindapur, Jhinukghata and Raynagar mouzas in reference to Gobindapur PWSS and Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) |  |  | ORD/000018/2025-2026 | 127/NAD-I | 22/04/2025 | 21/06/2025 | CHOWDHURY & CO. | 96.3 | 0 | 0 | 0
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Gobindapur at Hanskhali block by retrofitting of Ground Water Based PWSS for Gobindapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08815 | Retrofitting | Balance work for revamping / upgradation of the hydraulic parameters at Gobindapur Colony and Hijuli mauza in reference to Gobindapur PWSS and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission (Sl. NO. 08) |  |  | ORD/000051/2025-2026 | 231/NAD-I | 13/05/2025 | 12/07/2025 | TARUN GHOSH | 89.24 | 0 | 0 | 0
Total | [13 empty] | 343.89 | 141.5 | 41.15