## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08817 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000066/2021-2022 | 1420/NAD-I | 08/11/2021 | 07/01/2022 | CHAKRABORTTI ENTERPRISE | 68.76 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08817 | Retrofitting | Construction of Boundary wall & other allied works at 2nd Tubewell site of Ground water based piped supply scheme of Tarapur under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 57 metre. | Assistant Engineer-I | Junior Engineer-I | ORD/000132/2021-2022 | 75/NAD-I | 17/01/2022 | 06/02/2022 | M/S S.K ENTERPRISE | 6.9 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08817 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 144/NAD-I | 28/01/2022 | 28/01/2022 | Resource Division | 0.4 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08817 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Tarapur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Retrofitting under JJM of Tarapur (Part-I) Piped W/S Scheme (sl.no.14) | Assistant Engineer-I | Junior Engineer-I | ORD/000052/2023-2024 | 1429/NAD-I | 24/05/2023 | 08/06/2023 | SAORSA | 13.03 | 0 | 0 | 100
Total | [13 empty] | 89.09 | 0 | 0