## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-I, Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08819 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Bhayna Zone-I Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000117/2021-2022 | 10/NAD-I | 05/01/2022 | 05/04/2022 | TARUN KUMAR BHATTACHARYA | 202.09 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-I, Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08819 | Retrofitting | Retrofitting work at Bhayna Zone-I water supply scheme in Hanskhali Block in Nadia District under JJM under Nadia Arsenic Division-I , PHE Dte. | Assistant Engineer-I | Junior Engineer-IV | ORD/000170/2023-2024 | 427/AE-I/NAD-I | 20/09/2023 | 20/10/2023 | PALCON | 1.5 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-I, Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte | SM/08819 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 3005/NAD-I | 04/11/2022 | 04/11/2022 | Resource Division | 1.73 | 0 | 0 | 0
Total | [13 empty] | 205.32 | 0 | 0