## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08820 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000050/2021-2022 | 1407/NAD-I | 08/11/2021 | 07/01/2022 | M/S PRADIP KUMAR PAL | 69.04 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08820 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Augmentation of RAMNAGAR Water Supply Scheme in Hanskhali Block under Nadia Arsenic Division-1, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000122/2023-2024 | 318/AE-II/NAD-I | 14/07/2023 | 21/07/2023 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.4 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08820 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 3005/NAD-I | 04/11/2022 | 04/11/2022 | Resource Division | 1.73 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08820 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Ramnagar Ground Based Water Supply Scheme under Hnaskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Ramnagar (Part-I) under JJM (Sl.no.08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000111/2023-2024 | 1773/NAD-I | 26/07/2023 | 10/08/2023 | SUMAN CHAKRABORTY | 13.01 | 0 | 0 | 90
Total | [13 empty] | 88.18 | 0 | 0