## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08822 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000055/2021-2022 | 1412/NAD-I | 08/11/2021 | 07/01/2022 | H I ENTERPRISE | 87.11 | 83.82 | 96.22 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08822 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Saguna Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Saguna (Part-I) under JJM(Sl.no.12) | Assistant Engineer-I | Junior Engineer-II | ORD/000053/2023-2024 | 1426/NAD-I | 23/05/2023 | 07/06/2023 | ROY ASSOCIATES | 13.04 | 13.04 | 99.99 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08822 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 141/NAD-I | 28/01/2022 | 28/01/2022 | Resource Division | 0.2 | 0 | 0 | 0
Total | [13 empty] | 100.35 | 96.86 | 96.52