## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08824 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000053/2021-2022 | 1410/NAD-I | 08/11/2021 | 07/01/2022 | B.M. ENGINEERING & CONSTRUCTION | 86.04 | 84.75 | 98.5 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08824 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 140/NAD-I | 28/01/2022 | 28/01/2022 | Resource Division | 0.4 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08824 | Retrofitting | Laying of additional pipelines at Node Point 27 to 32 at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte | Assistant Engineer-II | Junior Engineer-IV | ORD/000037/2024-2025 | 185/AE-II/NAD-I | 09/08/2024 | 16/08/2024 | M/S ADIL CONSTRUCTION | 0.92 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08824 | Retrofitting | Interconnection between Common Manifold and distribution main at Bhayna Zone-I W/S Scheme under JJM in connection with Garapota and Bhayna W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. no. 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000051/2024-2025 | 1501/NAD-I | 18/09/2024 | 02/11/2024 | B.S. ENTERPRISE | 19.54 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08824 | Retrofitting | Laying of additional pipelines and reconnection of damages FHTC at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000036/2024-2025 | 184/AE-II/NAD-I | 09/08/2024 | 16/08/2024 | M/S ADIL CONSTRUCTION | 0.93 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Hanskhali Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08824 | Retrofitting | Laying of additional; pipelines at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000035/2024-2025 | 183/AE-II/NAD-I | 09/08/2024 | 16/08/2024 | M/S ADIL CONSTRUCTION | 0.92 | 0 | 0 | 100
Total | [13 empty] | 108.75 | 84.75 | 77.93