## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala, Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08829 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Dhantala Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000108/2021-2022 | 1610/NAD-I | 28/12/2021 | 28/03/2022 | UMWELT ENGINEER PVT. LTD. | 164.47 | 163.67 | 99.51 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala, Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08829 | Retrofitting | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) |  |  | ORD/000112/2025-2026 | 800/NAD-I | 18/08/2025 | 16/11/2025 | BIDYUT KUMAR | 182.15 | 0 | 0 | 0
Total | [13 empty] | 346.61 | 163.67 | 47.22