## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi | SM/08830 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-II (Hapania) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000109/2021-2022 | 1611/NAD-I | 28/12/2021 | 28/03/2022 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 404.05 | 389.71 | 96.45 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi | SM/08830 | Retrofitting | Laying UPVC pipeline at different location of Z-II ( Hapania ) under Nagarukhra -I & II G.P. under Surface Based Haringhata & Chakdah (Part) Surface Water Supply scheme under Nadia Arsenic -I, P.H.E. Dte. (01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000112/2022-2023 | 88 / AE-I/NAD-I | 28/04/2022 | 13/05/2022 | TARUN KUMAR BHATTACHARYA | 4.84 | 4.8 | 99.21 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi | SM/08830 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muratipur at Kanchrapara G.P. and Hapania at Nagrukhra-II G.P. by retrofitting of surface water based PWSS Water Supply Scheme for Haringhata-Chakdah (Part) in connection with retrofitting work of Zone-II, Hapania Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.02) | Assistant Engineer-I | Junior Engineer-II | ORD/000031/2023-2024 | 1255 /NAD-I | 04/05/2023 | 03/06/2023 | BUDDHADEV MONDAL | 37.15 | 37.14 | 99.97 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divisi | SM/08830 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II , Hapania at Nagarukhra G.P at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-II, Hapania, Part-III under Nadia Arsenic Division-I, PHE Dte. (sl. 18) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000221/2022-2023 | 303 /NAD-I | 27/02/2023 | 28/04/2023 | MONDAL ENTERPRISE | 96.62 | 0 | 0 | 74
Total | [13 empty] | 542.67 | 431.65 | 79.54