## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Chandmari), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi | SM/08833 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-IX (Chandmari) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000111/2021-2022 | 1613/NAD-I | 28/12/2021 | 28/03/2022 | SATYABRATA CHAKRABORTY | 248.68 | 247.52 | 99.53 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Chandmari), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi | SM/08833 | Retrofitting | Retrofitting work under Jal Jeevan Mission (JJM) for Zone-IX at North, South Chandmari, Muratipur at Kanchrapara G.P. by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) W/S Scheme for Zone-IX, Chandmari, Part-II under Nadia Arsenic Division-I , PHE Dte.(SL.06) | Assistant Engineer-I | Junior Engineer-I | ORD/000056/2023-2024 | 1465/NAD-I | 30/05/2023 | 20/06/2023 | BUDDHADEV MONDAL | 22.58 | 22.58 | 100 | 0
Total | [13 empty] | 271.26 | 270.1 | 99.57