## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi | SM/08836 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-X (Subarnapur) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000112/2021-2022 | 1614/NAD-I | 28/12/2021 | 28/03/2022 | GHOSH BROTHERS | 356.08 | 0 | 0 | 90
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi | SM/08836 | Retrofitting | Retrofitting work for Zone-IX (Chandmari) at Kanchrapara G.P. and Zone-X (Subarnapur) under Jal Jeevan Mission (JJM) by retrofitting of Surface Water Based PWSS for Haringhata & Chakdah (Part) for Zone-X (Subarnapur) Part-II under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (SL.03) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000236/2022-2023 | 501 / NAD-I | 10/03/2023 | 31/03/2023 | BUDDHADEV MONDAL | 30.99 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi | SM/08836 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Madanpur at Madanpur-I G.P by retrofitting of Surface Water based Piped Water Supply Scheme for Haringhata- Chakdah(Part) in connection with retrofitting work ofZone-X (Subarnapur),Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.13) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000022/2023-2024 | 1158 / NAD-I | 28/04/2023 | 19/05/2023 | CHOWDHURY & CO. | 92.76 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi | SM/08836 | Retrofitting | Jackpushing of Clear Water Rising Main at Majher Char Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000081/2023-2024 | 1702/NAD-I | 13/07/2023 | 03/08/2023 | M/S DIPAK ENTERPRISE | 89.84 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Divi | SM/08836 | Retrofitting | Jackpushing of Distribution Pipeline at Buddhapark Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000080/2023-2024 | 1701/NAD-I | 13/07/2023 | 07/08/2023 | M/S DIPAK ENTERPRISE | 93.64 | 0 | 0 | 100
Total | [13 empty] | 663.31 | 0 | 0