## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08840 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000119/2021-2022 | 12/NAD-I | 05/01/2022 | 05/04/2022 | UMWELT ENGINEER PVT. LTD. | 299.45 | 89.42 | 29.86 | 98
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08840 | Retrofitting | Repair of 800 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Barberia Zone-VIII under Surface W/S Scheme of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.05) | Assistant Engineer-I | Junior Engineer-I | ORD/000123/2022-2023 | 1385/NAD-I | 12/08/2022 | 26/09/2022 | TARUN KUMAR BHATTACHARYA | 32.36 | 32.3 | 99.81 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08840 | Retrofitting | Retrofitting work at Ghetugachi G.P for Surface water based P.W.S.S for Chakdah ( Part ) in connection with providing FHTC at Barberia ( Zone- VIII ) Part- II under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000091/2023-2024 | 1685/NAD-I | 12/07/2023 | 02/08/2023 | TAPAS GHOSH | 22.22 | 20.79 | 93.59 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08840 | Retrofitting | Interconnection in between outlet pipe of OHR and delivery main at different H/W site in Chakdah SurfaceWater Based PWSS at Chakdah Block under JJM under Nadia Arsenic Division-I,PHE Dte. (sl.15) | Assistant Engineer-II | Junior Engineer-IV | ORD/000259/2022-2023 | 826/NAD-I | 31/03/2023 | 15/05/2023 | BIPLAB GUHA | 39.73 | 36.71 | 92.38 | 58
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) underJaldhara / Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08840 | Retrofitting | Retrofitting work at Mukundupur of Balagarichar W/S Scheme and Dakshin Panchpota, Kadambagachi of Barberia W/S Scheme in connection with providing FHTC Zone-VIII (Barberia) Part-II under Barberia W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.10) | Assistant Engineer-II | Junior Engineer-III | ORD/000189/2023-2024 | 2154/NAD-I | 08/09/2023 | 11/10/2025 | SUMAN CHAKRABORTY | 91.29 | 54.84 | 60.07 | 100
Total | [13 empty] | 485.05 | 234.06 | 48.25