## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08841 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur, Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000064/2021-2022 | 1418/NAD-I | 08/11/2021 | 07/01/2022 | TAPU SAHA | 69.94 | 0 | 0 | 99
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08841 | Retrofitting | Retrofitting work at Haradham village under Parniamatpur W/S Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000192/2022-2023 | 84/AE-1/NAD-I | 03/02/2023 | 18/02/2023 | AURGHA BHATTACHARYA | 2.05 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08841 | Retrofitting | Retrofitting work at Rabonbor mouza near Sampa Biswas house and near Abodh Halder house under Parniamatpur Water Supply Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II under Nadia Arsenic Division-I, P.H.E. Dte. (SL No-2) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000188/2022-2023 | 85/AE-1/NAD-I | 06/02/2023 | 21/02/2023 | GANGULY ENTERPRISE | 4.83 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08841 | Retrofitting | Retrofitting work at Dakshin Haradham mouza (JI No 137) under Jal Jeevan Mission (JJM) for parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000003/2023-2024 | 165/AE-I/NAD-I | 11/04/2023 | 26/04/2023 | MS ENTERPRISE | 0.97 | 0 | 0 | 0
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08841 | Retrofitting | Retrofitting work at Paschim Sambhupur mouza (JI No 133) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2023-2024 | 163/AE-I/NAD-I | 10/04/2023 | 25/04/2023 | GANGULY ENTERPRISE | 0.97 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08841 | Retrofitting | Retrofitting work at Sibpur mouza (JI No 134) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground water based PWSS for parniamatpur Water Supply Scheme under Nadia Arsenic division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000002/2023-2024 | 164/AE-I/NAD-I | 10/04/2023 | 25/04/2023 | MS ENTERPRISE | 0.97 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08841 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 143/NAD-I | 28/01/2022 | 28/01/2022 | Resource Division | 0.8 | 0 | 0 | 0
Total | [13 empty] | 80.51 | 0 | 0