## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08843 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara/JalSwapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000074/2021-2022 | 1434/NAD-I | 09/11/2021 | 07/02/2022 | APURBA MANDAL | 117.48 | 115.42 | 98.25 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08843 | Retrofitting | Charges of entry of household date in JJM website along with Household Aadhar details and Geo tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(Sl No.-03) | Assistant Engineer-I | Junior Engineer-I | ORD/000282/2022-2023 | 309 / AE-I / NAD-I | 30/12/2022 | 30/03/2023 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08843 | Retrofitting | Retrofitting work at Rabonbor mouza near Shyamal Biswas house and near Sailen Halder house under Parniamatpur Water Supply Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000189/2022-2023 | 86/AE-I/NAD-I | 06/02/2023 | 21/02/2023 | BISWAS CONSTRUCTION | 4.64 | 4.64 | 100 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08843 | Retrofitting | Charges of entry of household date in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(sl.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000250/2022-2023 | 241 / AE-I / NAD-I | 29/09/2022 | 28/12/2022 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08843 | Retrofitting | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division- I, P.H.E. Dte. for the period from 15.07.2021 to 14.07.2022 i.e. for 1(one) year. | Assistant Engineer-I | Junior Engineer-I | ORD/000321/2021-2022 | 129 /AE-I/NAD-I | 14/07/2021 | 14/07/2022 | SUMAN CHAKRABORTY | 4.27 | 4.16 | 97.42 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08843 | Retrofitting | Retrofitting work at Nandighat mouza (Jl No 126) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer-I | Junior Engineer-I | ORD/000194/2023-2024 | 2240/NAD-I | 21/09/2023 | 12/10/2023 | GANGULY ENTERPRISE | 11.86 | 11.86 | 100 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08843 | Retrofitting | Retrofitting work under Jal Jeevan Mission (JJM) at Nandighat, Sardarpara & Baganpara under Anulia G.P. under Parniamatpur Phase-II at Ranaghat-I Block by retrofitting Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.06) | Assistant Engineer-I | Junior Engineer-I | ORD/000191/2023-2024 | 2206/NAD-I | 13/09/2023 | 28/09/2023 | SAORSA | 42.45 | 42.25 | 99.52 | 100
Total | [13 empty] | 190.41 | 188.03 | 98.75