## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08844 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000123/2021-2022 | 48/NAD-I | 11/01/2022 | 11/04/2022 | M/S MALLICK ENTERPRISE | 126.06 | 125.49 | 99.55 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08844 | Retrofitting | Laying of additional pipelines and other allied works Chupria Zone-II W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000039/2024-2025 | 1315/NAD-I | 22/08/2024 | 31/08/2025 | MS MAA BHABANI ENTERPRISE | 9.72 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08844 | Retrofitting | Interconnection between Manifold and delivery main and approach road at arranghata Zone-I W/S Scheme in Ranaghat-II block and Chupria Zone-I in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000138/2024-2025 | 2006/NAD-I | 29/11/2024 | 16/08/2025 | BUDDHADEV MONDAL | 40.2 | 0 | 0 | 50
Total | [13 empty] | 175.98 | 125.49 | 71.31