## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi | SM/08846 | Retrofitting | Construction of Boundary wall, pathway and others allied works at Head Work site of Goalsalua, Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. Length of Boundary wall - 156 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000133/2021-2022 | 73/NAD-I | 17/01/2022 | 16/02/2022 | D.K. CONSTRUCTION | 17.59 | 0 | 0 | 95
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi | SM/08846 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Goalsalua Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000129/2021-2022 | 77/NAD-I | 17/01/2022 | 17/04/2022 | M/S NIBHAS SINHA | 110.34 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi | SM/08846 | Retrofitting | Augmentaton of Distribution pipeline at Rajapur , Kesaipur village under Goalsalua Zone II water supply scheme at Ranaghat-II Block by providing FHTCs & dedicated pipeline from common manifold under Nadia Arsenic Division-I, PHE Dte as a part of JJM. (Sl. NO. 05) |  |  | ORD/000170/2024-2025 | 2057/NAD-I | 09/12/2024 | 07/02/2025 | SUMIT GHOSH | 91.9 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi | SM/08846 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Goalsalua Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Goalsalua Zone-II under JJM (Sl.no.07) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000055/2023-2024 | 1458/NAD-I | 29/05/2023 | 13/06/2023 | ROY ASSOCIATES | 13.04 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofi | SM/08846 | Retrofitting | Laying Dedicated Pipe line to supply water for Pachberia Coloni Area under Goalsalua Zone II Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 06) | Assistant Engineer-II | Junior Engineer-II | ORD/000168/2024-2025 | 1949/NAD-I | 27/11/2024 | 26/01/2025 | BIPLAB GUHA | 70.82 | 0 | 0 | 52
Total | [13 empty] | 303.69 | 0 | 0