## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit | SM/08847 | Retrofitting | Construction of Boundary wall at H/W site of Goalsalua, Zone-I Water Supply Scheme under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 208 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000131/2021-2022 | 72/NAD-I | 17/01/2022 | 16/02/2022 | NISHITH BANERJEE | 19.68 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit | SM/08847 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua, Zone-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Goalsalua Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000046/2021-2022 | 1403/NAD-I | 08/11/2021 | 23/12/2021 | BIDYUT KUMAR | 53.89 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit | SM/08847 | Retrofitting | Laying of additional pipeline for providing FHTC (Functional Household Tap Connection)at Salua Gatepara & pipeline connection with Manifold under JJM at Ranaghat-II Block of Ground Water Based PWSS for Goalsalua Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000165/2024-2025 | 327/AE-II/NAD-I | 09/12/2024 | 24/12/2024 | GOUTAM DEY | 4 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit | SM/08847 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Goalsalua Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Goalsalua Zone-I under JJM.(sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000041/2023-2024 | 1123 / NAD-I | 27/04/2023 | 12/05/2023 | MANAJIT BISWAS | 13.03 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit | SM/08847 | Retrofitting | Balance work for revamping/upgradation of the hydraulic parameters at Hatisala and Goalsalua mouzas in reference to Goalsalua mouzas in reference to Goalsalua W/S Scheme under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 03) |  |  | ORD/000036/2025-2026 | 170/NAD-I | 29/04/2025 | 28/06/2025 | PAPAN ROY | 44.03 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-I Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block by retrofit | SM/08847 | Retrofitting | Jackpushing & other allied works near Bankim Nagar station (BNCA to PNCB) in between Mast No - 77/24 and 77/26 in the district of Nadia to provide FHTC at Kesaipur under Goalsalua PWSS under Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. (2nd Call) [Sl. No. 03] |  |  | ORD/000141/2025-2026 | 1042/NAD-I | 25/09/2025 | 24/12/2025 | SUMAN CHAKRABORTY | 39.44 | 0 | 0 | 0
Total | [13 empty] | 174.08 | 0 | 0