## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08849 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000093/2021-2022 | 1541/NAD-I | 06/12/2021 | 06/03/2022 | JOY HIND TUBE WELLS | 123.89 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08849 | Retrofitting | Providing FHTC (Functional Household Tap Connection) at Patkabari, Hatibanda and Uttor Bishnupur under Jaldhara Jal Swapna from Arranghata Zone-I PWSS Part-III at Ranaghat-II Block by retrofitting under under Nadia Arsenic Division- I, P.H.E Dte. (Sl. No. 14) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000130/2022-2023 | 3044/NAD-I | 09/11/2022 | 09/12/2022 | M/S R.K. ENTERPRISE | 32.39 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08849 | Retrofitting | Construction of Boundary wall, Toilet, Pathway OHR Repair and other allied work in connection with Augmentation of Arranghata Zone-I water supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. (sl.no.16) | Assistant Engineer-II | Junior Engineer-IV | ORD/000244/2022-2023 | 569/NAD-I | 16/03/2023 | 15/05/2023 | REAL TIME | 59.28 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08849 | Retrofitting | Construction of Boundary wall and pathway and Toilet at 2nd, 3rd and 4th Tubewell site of Aranghata and 3rd site of Debogram water supply Scheme in Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Under JJM. (Sl. No. 09) |  |  | ORD/000029/2025-2026 | 155/NAD-I | 28/04/2025 | 27/06/2025 | GOUTAM DEY | 34.34 | 0 | 0 | 0
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08849 | Retrofitting | Work for revamping / upgradation of the hydraulic parameters at Head work site to Shibnarayanpur and allied works in reference to Aranghata Zone-I water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (2nd Call) [Sl. No. 04] | Assistant Engineer-II | Junior Engineer-IV | ORD/000106/2025-2026 | 720/NAD-I | 29/07/2025 | 27/09/2025 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 49.04 | 0 | 0 | 0
Total | [13 empty] | 298.94 | 0 | 0