## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08851 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1961/NAD-I | 18/08/2023 | 18/08/2023 | Resource Division | 24.52 | 0 | 0 | 0
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08851 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-II W/S Scheme, Phase-II at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000002/2022-2023 | 643/NAD-I | 29/04/2022 | 28/07/2022 | UNICON INDIA | 335.39 | 0 | 0 | 10
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08851 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenatioin under Jal Jeevan Mission Aranghata Zone- II W/S Scheme, Part - II at Ranaghat- II Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000104/2023-2024 | 1696/NAD-I | 13/07/2023 | 02/09/2025 | ORIENT CONSTRUCTION | 311.77 | 207.55 | 66.57 | 90
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08851 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Dhara / Jal Swapna for Aranghata Zone-II Part -III under Jal Jeevan Mission at Ranaghat -II Block by retrofitting of ground Water based PWSS for Aranghata Zone-II Water Supply Scheme under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000355/2023-2024 | 461/NAD-I | 15/03/2024 | 01/04/2025 | DIVINE | 329.47 | 0 | 0 | 75
Total | [13 empty] | 1001.15 | 207.55 | 20.73