## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Purba Bishnupur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/08852 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-V,(Purba Bishnupur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000121/2021-2022 | 14/NAD-I | 05/01/2022 | 05/04/2022 | M/S TARAK CHANDRA PAUL | 277.36 | 277.33 | 99.99 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Purba Bishnupur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE | SM/08852 | Retrofitting | Retrofitting work for Purba Bishnupur Zone V of Surface Water based PWSS for Chakdah Part water supply scheme under NAD - I PHE Dte (SL.06) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000256/2022-2023 | 1473 / NAD-I | 22/08/2022 | 21/10/2022 | APURBA MANDAL | 32.4 | 27.39 | 84.54 | 100
Total | [13 empty] | 309.76 | 304.72 | 98.37