## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VI, (Balia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08853 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-VI (Balia), Part-II at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000096/2021-2022 | 1565/NAD-I | 13/12/2021 | 13/03/2022 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 214.98 | 204.67 | 95.2 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VI, (Balia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08853 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-IV, Balia (Part-II) at Chak Amdanga, Silinda, Balia, Balarampur village at Chakdah Block retrofitting of Surface Water Based PWSS FOR Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (SL.NO.10) | Assistant Engineer-I | Junior Engineer-II,Junior Engineer-IV | ORD/000145/2022-2023 | 3216/NAD-I | 30/11/2022 | 30/12/2022 | BIDYUT KUMAR | 31.54 | 29.46 | 93.4 | 100
Total | [13 empty] | 246.52 | 234.12 | 94.97