## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna Programme covering Mashunda Village by retrofitting of Paschim Noapara Water Supply Scheme under Ranaghat-I Block under Nadia District under Nadia Arsenic Division-I, PHE Dte | SM/08854 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Masunda village at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000065/2021-2022 | 1419/NAD-I | 08/11/2021 | 07/01/2022 | PRIYA CONSTRUCTION | 77.38 | 75.9 | 98.09 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna Programme covering Mashunda Village by retrofitting of Paschim Noapara Water Supply Scheme under Ranaghat-I Block under Nadia District under Nadia Arsenic Division-I, PHE Dte | SM/08854 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Paschim Noapara at Ranaghat-I Block by augmentation of Ground Water Based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte . (Sl.no.12) | Assistant Engineer-I | Junior Engineer-I | ORD/000221/2023-2024 | 2409/NAD-I | 10/10/2023 | 09/11/2023 | JOYGOPAL GUPTI | 86.45 | 86.09 | 99.58 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna Programme covering Mashunda Village by retrofitting of Paschim Noapara Water Supply Scheme under Ranaghat-I Block under Nadia District under Nadia Arsenic Division-I, PHE Dte | SM/08854 | Retrofitting | "Augmentation of pipeline damaged due to construction of drain including new pipeline and FHTC connection at Sundalpur Char, Paschim Noapara, Sahebdanga, Paschim Noapara villages under Paschim Noapara PWSS and Gosaichar village under Gosaichar Water Supply Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (S1. No. 01)" | Assistant Engineer-I | Junior Engineer-I | ORD/000139/2024-2025 | 2005/NAD-I | 29/11/2024 | 28/05/2025 | M/S DIPAK ENTERPRISE | 24.76 | 0 | 0 | 100
Total | [13 empty] | 188.59 | 161.98 | 85.89