## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna Programme covering Mashunda Village by retrofitting of Paschim Noapara Water Supply Scheme under Ranaghat-I Block under Nadia District under Nadia Arsenic Division-I, PHE Dte | SM/08854 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Masunda village at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000065/2021-2022 | 1419/NAD-I | 08/11/2021 | 07/01/2022 | PRIYA CONSTRUCTION | 77.38 | 75.9 | 98.09 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna Programme covering Mashunda Village by retrofitting of Paschim Noapara Water Supply Scheme under Ranaghat-I Block under Nadia District under Nadia Arsenic Division-I, PHE Dte | SM/08854 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Paschim Noapara at Ranaghat-I Block by augmentation of Ground Water Based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte . (Sl.no.12) | Assistant Engineer-I | Junior Engineer-I | ORD/000221/2023-2024 | 2409/NAD-I | 10/10/2023 | 09/11/2023 | JOYGOPAL GUPTI | 86.45 | 86.09 | 99.58 | 100
Total | [13 empty] | 163.83 | 161.98 | 98.87