## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli Zone-I, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08856 | Retrofitting | Providing Functioanal Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Dubli, Zone-I at Ranaghat-II Block by retrofitting of GRound Water based PWSS for Dubli, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000105/2021-2022 | 1587/NAD-I | 22/12/2021 | 22/03/2022 | SUPRITI ENTERPRISE | 205.54 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli Zone-I, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08856 | Retrofitting | Construction of Boundary wall and pathway Head work site of Duttaphulia Zone- II and Dubli Zone- I water supply Scheme in Ranaghat-II Block in connection with Duttaphulia Zone-I W/S Scheme under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (sl.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000019/2025-2026 | 137/NAD-I | 23/04/2025 | 22/06/2025 | CFS MANAGEMENT PRIVATE LIMITED | 38.99 | 0 | 0 | 0
Total | [13 empty] | 244.53 | 0 | 0