## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08859 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000128/2021-2022 | 53/NAD-I | 11/01/2022 | 11/04/2022 | TIRUPATI ENTERPRISES | 163.2 | 155.42 | 95.23 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08859 | Retrofitting | Retrofitting work at Mamjoani (Part-I) W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000156/2022-2023 | 225/AE-II/NAD-I | 07/12/2022 | 22/12/2022 | PURNIMA ELECTRICS & DECORATORS | 2.59 | 2.58 | 99.6 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08859 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000004/2025-2026 | 39/NAD-I | 07/04/2025 | 05/12/2025 | REAL TIME | 39.28 | 0 | 0 | 50
Total | [13 empty] | 205.08 | 158.01 | 77.05