## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000080/2021-2022 | 1448/NAD-I | 12/11/2021 | 10/02/2022 | DIVINE | 151.18 | 150.68 | 99.66 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Construction of Boundary wall, pathway and other allied works at Head Work Tubewell site of Ground water based piped supply scheme of Halalpur-Krishnapur Zone-I Piped Water Supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 138 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000134/2021-2022 | 76/NAD-I | 17/01/2022 | 06/02/2022 | MONDAL ENTERPRISE | 9.94 | 3.22 | 32.4 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Repairing and renovation of Rising main and allied works at Halalpur Krishnapur Zone-I under Ranaghat-II, Block under Halalpur Krishnapur Zone-I Water Supply Scheme in the District of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000110/2022-2023 | 253/AE-I/NAD-I | 21/10/2022 | 05/11/2022 | BUDDHADEV MONDAL | 0.93 | 0.92 | 99.8 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Laying of UPVC pipe line at Jaffarnagar ,near Headwork Site under Raghunathpur Hijuli-I Gram Panchayet under Halalpur Zone-I Water Supply Scheme under Ranahghat -II Block under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000113/2022-2023 | 254/AE-I/NAD-I | 21/10/2022 | 05/11/2022 | BUDDHADEV MONDAL | 0.96 | 0.96 | 99.85 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Laying of UPVC pipeline and retrofitting work at different loations i.e; Halalpur Krishnapur ,Madanpur,Goalpur,Beharia and Nabla Mouzas for smooth water supply in coneection with Retrofitting under JJM of Ground Water Based PWSS of Halalpur Krishnapur Zone-I W/S Scheme at Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E Dte.(sl.no.14) | Assistant Engineer-II | Junior Engineer-III | ORD/000014/2023-2024 | 11118 / NAD-I | 27/04/2023 | 18/05/2023 | CHOWDHURY & CO. | 23.38 | 23.38 | 99.99 | 0
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II form Puratan Chapra Primary School to Kharida Chapra Primary School at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000175/2022-2023 | 57/AE-I/NAD-I | 17/01/2023 | 01/02/2023 | BANERJEE ENTERPRISE | 3.88 | 3.6 | 92.7 | 99
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Pragati Sangha Club to Purba Para Kalimandir at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000264/2022-2023 | 142/AE-I/NAD-I | 29/03/2023 | 13/04/2023 | CONSTRUCTURE | 3.63 | 3.63 | 99.97 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Purba Para Kalimandir to Paschim Sangha at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000265/2022-2023 | 143/AE-I/NAD-I | 29/03/2023 | 13/04/2023 | CONSTRUCTURE | 3.38 | 3.38 | 100 | 100
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I,Construction of Arsenic-cum Iron Removal Plant (AIRP), Boundary Wall, pathway and other allied works at H/W site of this at Ranaghat-II Block | SM/08860 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 147/NAD-I | 28/01/2022 | 28/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
Total | [13 empty] | 199.27 | 189.76 | 95.23