## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08862 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000073/2021-2022 | 1414/NAD-I | 08/11/2021 | 23/12/2021 | JOY HIND TUBE WELLS | 44.57 | 44.25 | 99.28 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08862 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 142/NAD-I | 28/01/2022 | 28/01/2022 | Resource Division | 0.4 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | SM/08862 | Retrofitting | Interconnection between 1st and 2nd Tubewell Rising Main at Chupria Zone-II W/S Scheme in Hanskhali block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000214/2023-2024 | 2371/NAD-I | 06/10/2023 | 27/10/2023 | BISWAS CONSTRUCTION | 14.67 | 13.26 | 90.42 | 100
Total | [13 empty] | 59.63 | 57.51 | 96.44