## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-XII (BALAGARICHAR), WTP & INTAKE at Chakdaha Block, by retrofitting of | SM/09936 | Augmentation | Repair Renovation of Chakdah WTP and intake with different units and Boundary Wall of WTP under Surface W/S Scheme of Chakdah (Part) block under Nadia Arsenic Division-I PHE Dte (Sl. NO. 09) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000037/2022-2023 | 1533/NAD-I | 31/08/2022 | 30/10/2022 | PALCON | 52.63 | 0 | 0 | 95
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-XII (BALAGARICHAR), WTP & INTAKE at Chakdaha Block, by retrofitting of | SM/09936 | Augmentation | Phase-III FHTC ((Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XII, (Balagarichar) at Chakdah Block by retrofitting of Surface Water Based PWSS for Chakdah (Part) Water Supply under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000129/2022-2023 | 3043/NAD-I | 09/11/2022 | 24/12/2022 | M/S A.K. CONSTRUCTION | 33.39 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-XII (BALAGARICHAR), WTP & INTAKE at Chakdaha Block, by retrofitting of | SM/09936 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at BalagariChar Zone-XII under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte (Sl.no.03) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000079/2022-2023 | 1763 / NAD-I | 19/09/2022 | 03/11/2022 | BISHALAXMI ENTERPRISE | 20.08 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-XII (BALAGARICHAR), WTP & INTAKE at Chakdaha Block, by retrofitting of | SM/09936 | Augmentation | Interconnection between node point 3 and 76 of Balagarichar W/S Scheme for augmentation work at Uttar Ghughia village under Chakdah (Part) Water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000079/2023-2024 | 1412/NAD-I | 18/05/2023 | 17/06/2023 | MESSRS FREEDOM CONSTRUCTION | 62.36 | 0 | 0 | 100
Total | [13 empty] | 168.47 | 0 | 0