## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of RUKMINIDANGA (ZONE-IV) at Chakdaha Block, District-Nadia of Surface Water based PWSS for Chakdaha (Part) for FHTC (Functional Household Tap Con | SM/09937 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Rukminidanga ZoneV at under Chakdah Surface WS Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000060/2022-2023 | 1596/NAD-I | 06/09/2022 | 05/11/2022 | SAHA ENGINEERS | 28.04 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of RUKMINIDANGA (ZONE-IV) at Chakdaha Block, District-Nadia of Surface Water based PWSS for Chakdaha (Part) for FHTC (Functional Household Tap Con | SM/09937 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1781/NAD-I | 22/09/2022 | 22/09/2022 | Resource Division | 26.12 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of RUKMINIDANGA (ZONE-IV) at Chakdaha Block, District-Nadia of Surface Water based PWSS for Chakdaha (Part) for FHTC (Functional Household Tap Con | SM/09937 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-IV, (Rukminidanga), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000003/2022-2023 | 644/NAD-I | 29/04/2022 | 31/03/2023 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 359.23 | 0 | 0 | 100
Total | [13 empty] | 413.39 | 0 | 0