## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Div | SM/09938 | Augmentation | Repair, Renovation of Haringhata WTP (including 500 cum Back Wash OHR) and Intake with different units and Boundary Wall of WTP under Surface W/S Scheme Haringhata-Chakdah (Part) under Nadia Arsenic Division-I PHE Dte (Sl.no. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000122/2022-2023 | 1908 / NAD-I | 29/09/2022 | 28/11/2022 | TARUN KUMAR BHATTACHARYA | 55.33 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Div | SM/09938 | Augmentation | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Darrappur, Zone-V under Surface W/S Scheme of Haringhata-Chakdah (Part) under NAD I PHE Dte (Sl.no. 13) | Assistant Engineer-I | Junior Engineer-I | ORD/000146/2022-2023 | 3217/ NAD-I | 30/11/2022 | 14/01/2023 | CHANDAN ROY | 14.38 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Div | SM/09938 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V (Darrappur) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 10) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-IV | ORD/000159/2021-2022 | 426/NAD-I | 07/03/2022 | 06/05/2022 | NATIONAL CONSTRUCTION | 93.56 | 0 | 0 | 100
Total | [13 empty] | 163.27 | 0 | 0