## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Chandmari) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 14) | Assistant Engineer-II | Junior Engineer-III | ORD/000175/2021-2022 | 466/NAD-I | 10/03/2022 | 09/05/2022 | CALCON CONSTRUCTION | 91.89 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XII (Madanpur) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000173/2021-2022 | 464/NAD-I | 10/03/2022 | 09/05/2022 | H I ENTERPRISE | 93.56 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Repair of 700 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Chandmari Zone-XI under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000143/2022-2023 | 3154 / NAD-I | 25/11/2022 | 24/01/2023 | NEERMAN | 25.87 | 0 | 0 | 99
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XII at Madanpur I & II G.P at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XII, Madanpur,Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000176/2022-2023 | 34/NAD-I | 17/01/2023 | 18/03/2023 | CHOWDHURY & CO. | 96.1 | 0 | 0 | 90
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Repair of 410 cum Over Head Reservoir (Two Nos) Painting and repairing of H/W Boundary Wall, Pump House at Madanpur Zone-XII under Surface W/S Scheme Haringhata-Chakdah (Part) under Nadia Arsenic Division-I PHE Dte. (Sl.no.04) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000070/2022-2023 | 1692 / NAD-I | 08/09/2022 | 23/10/2022 | CHOWDHURY & CO. | 36.08 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Augmentation work for Zone-XII (Madanpur) at Madanpur G.P at Chakdah block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata-Chakdah (Part) for Zone-XII (Madanpur) Part-III under Nadia Arsenic Division-I, PHE Dte. (SL no-01) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000171/2022-2023 | 37/AE-I/NAD-I | 07/01/2023 | 22/01/2023 | BUDDHADEV MONDAL | 4.84 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Madanpur at Madanpur-I G.P by retrofitting of Surface Water based Piped Water Supply Scheme for Haringhata- Chakdah(Part) in connection with retrofitting work ofZone-X (Subarnapur),Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.13) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000022/2023-2024 | 1158 / NAD-I | 28/04/2023 | 19/05/2023 | CHOWDHURY & CO. | 92.76 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Jackpushing of Clear Water Rising Main at Majher Char Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000081/2023-2024 | 1702/NAD-I | 13/07/2023 | 03/08/2023 | M/S DIPAK ENTERPRISE | 89.84 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Water Supply Arrangement in High School, PrimarySchool, SSk & MSK under Jal Jeevan Mission (JJM) atHaringhata Block under Zone-IX (Chandmari) underAugmentation of Zone-IV (Chandmari) & Zone-XIIMadanpur, Part-III at Surface Water Based Water Suupply Scheme of Haringhata & Chakdah (Part)Water Supply Scheme of Haringhata & Chakdah (Part)under Nadia Arsenic Division-I, PHE Dte. (SL.NO.05) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000207/2022-2023 | 178/ NAD-I | 09/02/2023 | 02/03/2023 | M/S KALIMATA ENTERPRISE | 20.46 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Grouting and Renovation of 700 cum capacity OverHead Reservoir at Chandmari,Zone-IX under Surface water supply scheme of Haringhata-Chakdah(Part) under Nadia Arsenic Division - I P. H.E. Dte (Sl. NO. 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000198/2023-2024 | 469/AE-I/NAD-I | 09/10/2023 | 08/11/2023 | NEERMAN | 4.79 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Providing domestic Water Supply to the 36 nos. temporary dwelling units constructed near Buddha Park, Kalyani for rehabilitation of families of Majher Char area including W/S at Sahidpally and Majherchar at Kanchrapara GP at Kalyani block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) W/S Scheme for Zone-XI Chandmari under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000232/2023-2024 | 2300/NAD-I | 29/09/2023 | 20/10/2023 | M/S DIPAK ENTERPRISE | 12.7 | 0 | 0 | 100
12 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme u | SM/09939 | Augmentation | Road Restoration under for Madanpur-I and Madanpur-II GP at Kalyani Block under providing FHTC (Functional Household Tap Connection) under Jaldhara/Jalswapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 06) | Assistant Engineer-I | Junior Engineer-I | ORD/000032/2025-2026 | 166/NAD-I | 29/04/2025 | 29/05/2025 | MANAJIT BISWAS | 31.06 | 0 | 0 | 100
Total | [13 empty] | 599.96 | 0 | 0