## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09940 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VIII (Tarinipur) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000155/2021-2022 | 422/NAD-I | 07/03/2022 | 06/05/2022 | M/S K.P. CONSTRUCTION | 73.17 | 67.83 | 92.7 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09940 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone- VII, Kumarpur Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 15) | Assistant Engineer-II | Junior Engineer-III | ORD/000172/2021-2022 | 439/NAD-I | 07/03/2022 | 21/04/2022 | MALI CONSTRUCTION | 39.65 | 39.62 | 99.92 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09940 | Augmentation | Shifting of different dia D.I pipe and HDPE Pipe from the Office Premises of Nadia Arsenic Division -I to nearest Zone-VIII (Tarinipur) OHR site under Haringhata and Chakdah (Part) Surface Based W/S Scheme at Chakdah Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000135/2022-2023 | 267/AE-I/NAD-I | 09/11/2022 | 24/11/2022 | BUDDHADEV MONDAL | 3.46 | 3.46 | 100 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09940 | Augmentation | Repair of 900 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Tarinipur, Zone-VIII under Surface W/S Scheme of Haringhata- Chakdah (Part) under Nadia Arsenic Division-I PHE Dte (Sl.no.08) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000058/2022-2023 | 1639 / NAD-I | 06/09/2022 | 05/11/2022 | REAL TIME | 33.3 | 30.74 | 92.3 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09940 | Augmentation | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Kumarpur, Zone-VII under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I P.H.E Dte. (Sl. No. 12) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000103/2022-2023 | 2064/NAD-I | 28/10/2022 | 12/12/2022 | GANGULY ENTERPRISE | 13.95 | 13.92 | 99.74 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09940 | Augmentation | Augmentation work at Zone-VIII (Tarinipur) under Augmentation work of Zone-VII (Kumarpur) and Zone-VIII (Tarinipur), Part-III at Santipur Block under Surface Water Based PWSS for Haringhata & Chakdah(Part) under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000197/2023-2024 | 2242/NAD-I | 21/09/2023 | 06/10/2023 | NISHITH BANERJEE | 12.9 | 12.9 | 99.99 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09940 | Augmentation | Laying of UPVC Pipeline and other allied works under JJM at Khalderpara, Babudangapara for Kumarpur Zone-VII at Haringhata Block by retrofitting work of Surface based W/S Scheme Water PWSS of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000242/2023-2024 | 529/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | M/S K..M. ENTERPRISE | 4.36 | 4.35 | 99.72 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -VII, (Kumarpur), Zone-VIII, (Tarinipur), Part-III at Chakdah Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09940 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) incluidng restoration of road for Tarinipur at Sarati G.P. at Kalyani under Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000243/2023-2024 | 530/AE-I/NAD-I | 24/11/2023 | 24/12/2023 | M/S S.K ENTERPRISE | 4.85 | 4.84 | 99.95 | 100
Total | [13 empty] | 185.65 | 177.66 | 95.7