## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. | SM/09941 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Gobindapur Zone-II at Santipur Block by retrofitting of Ground Water based PWSS for Gobindapur W/S Scheme under Nadia Arsenic Division-I, P.H.E Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-II,Junior Engineer-III | ORD/000008/2022-2023 | 765/NAD-I | 07/06/2022 | 05/09/2022 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 637.9 | 632.37 | 99.13 | 100
2 | NADIA |  | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. | SM/09941 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1781/NAD-I | 22/09/2022 | 22/09/2022 | Resource Division | 28.78 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. | SM/09941 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1961/NAD-I | 18/08/2023 | 18/08/2023 | Resource Division | 12.69 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. | SM/09941 | Retrofitting | Construction and installation of MANIFOLD and allied works at OHR site under Gobindapur Zone-II Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Retrofitting under JJM under Gobindapur Zone-II Piped W/S Scheme (Sl.no.32) | Assistant Engineer-I | Junior Engineer-II | ORD/000043/2023-2024 | 1363/ NAD-I | 12/05/2023 | 27/05/2023 | SANDIP ROY | 12.75 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. | SM/09941 | Retrofitting | Repair of 550 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House repair, Construction of Rigid Pavement and Boundary Wall for 2nd & 3rd T/W site at Gobindapur Zone-II Water Supply Scheme in Santipur Block under Nadia Arsenic Division-I, PHE Dte. (sl.no.14) | Assistant Engineer-I | Junior Engineer-II,Junior Engineer-III | ORD/000154/2022-2023 | 3448 / NAD-I | 21/12/2022 | 11/04/2027 | THE CALCUTTA CONSTRUCTION | 38.03 | 14.71 | 38.69 | 100
6 | NADIA |  | Nadia Arsenic Division I | Detailed Project Report on retrofitting of Ground Water Based Piped Water Supply Scheme for GOBINDAPUR ZONE-II BLOCK-Santipur, Dist-Nadia. | SM/09941 | Retrofitting | "Retrofitting work at villages Batangachi, Barajiakur and Bagdiain connection with Retrofitting of Ground Water Based PWSS for Goibindapur Zone-II at Santipur Block under Nadia Arsenic Division-I,PHE Dte."(Sl.no.02) | Assistant Engineer-I | Junior Engineer-II | ORD/000071/2023-2024 | 1380/NAD-I | 15/05/2023 | 09/07/2026 | SAHA ENGINEERS | 60.15 | 0 | 0 | 26
Total | [13 empty] | 790.29 | 647.08 | 81.88