## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Paschim Noapara, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000180/2021-2022 | 517/NAD-I | 28/03/2022 | 27/05/2022 | GHOSH BROTHERS | 171.71 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Saguna Part-III at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-I | Junior Engineer-I | ORD/000169/2021-2022 | 437/NAD-I | 07/03/2022 | 06/05/2022 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 63.41 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Construction of Boundary wall, Pathway and all repair works at 2nd T/W Site and all repair works at H/W site of Saguna under Nadia Arsenic Division-I, PHE Dte. ( Sl.no 11) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000053/2022-2023 | 1592 / NAD-I | 06/09/2022 | 21/10/2022 | PAPAN ROY | 11.31 | 0 | 0 | 85
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Construction of Boundary Wall, Pathway and all repair works at 2nd T/W site and all repair works at H/W site of Paschim Noapara W/S Scheme under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000111/2022-2023 | 2009/NAD-I | 19/10/2022 | 18/11/2022 | J & T ENTERPRISE | 6.93 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Repair of 450 cum capacity Over Head Reservoir and other allied works at Saguna WS Scheme in Santipur Block under NAD I PHE Dte (Sl.no.04) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000105/2022-2023 | 2049 / NAD-I | 21/10/2022 | 05/12/2022 | M/S ARATI ENTERPRISE | 14.01 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Repair of 350 cum capacity Over Head Reservoir and other allied works at Paschim Noapara W/S Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte.(Sl.no.07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000069/2022-2023 | 1443/NAD-I | 17/09/2022 | 01/11/2022 | MONDAL ENTERPRISE | 12.83 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Pipeline connection with Manifold to dedicated line under Jal Jeevan Mission (JJM) at Shantipur Block under Ground Water based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000302/2023-2024 | 95/AE-I/NAD-I | 27/02/2024 | 13/03/2024 | ROY ASSOCIATES | 2.89 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Hijuli, Ghoshpara, Aluipara & adjacent areas of Shantipur Block by retrofitting of Ground Water Based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000273/2023-2024 | 2744/NAD-I | 08/12/2023 | 23/12/2023 | DEBASIS SAMADDAR | 57.4 | 0 | 0 | 70
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PASCHIM NOAPARA of Ranaghat-I Block, & SAGUNA of Santipur Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Re | SM/09957 | Augmentation | Retrofitting pipeline works for providing FHTC (Functional Household Tap Connection) at Aluipara & Srirampur para under JJM at Shantipur Block of Ground Water Based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-I | Junior Engineer-II | ORD/000057/2024-2025 | 1543/NAD-I | 23/09/2024 | 02/11/2025 | TAPAS GHOSH | 10.69 | 0 | 0 | 80
Total | [13 empty] | 351.18 | 0 | 0