## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Dhantala W/S Scheme within Ranaghat -II Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl.no. 02) | Assistant Engineer-II | Junior Engineer-III | ORD/000040/2022-2023 | 1582 /NAD-I | 06/09/2022 | 21/10/2022 | GHOSH CONSTRUCTION | 24.96 | 20.22 | 80.98 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Dhantala WS Scheme atRanaghat II Block under NAD I PHE Dte(sl.no.02) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000138/2022-2023 | 3037/NAD-I | 09/11/2022 | 24/12/2022 | TAPU SAHA | 25.33 | 25.28 | 99.8 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Construction of Boundary Wall Toilet Pathway and other allied work at Sabdalpur W S Scheme within Ranaghat II Block under NAD I PHE Dte. (sl.no.04) | Assistant Engineer-II | Junior Engineer-II | ORD/000133/2022-2023 | 3034/NAD-I | 09/11/2022 | 24/12/2022 | M/S LAXMI ENTERPRISE | 12.78 | 9.05 | 70.82 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Repair of 350 cum capacity Over Head Reservoir Painting and repairing of H W Boundary Wall Pump House and AIRP at Sabdalpur W/S Scheme at Ranaghat-II Block under Nadia Arsenic Division-I P.H.E Dte (Sl.No.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000132/2022-2023 | 3045/NAD-I | 09/11/2022 | 24/12/2022 | MONDAL CONSTRUCTION | 31.43 | 26.84 | 85.39 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Retrofitting Work for Provoiding FHTC at Bholadanga under Jal Jeevan Mission (JJM) at Ranaghat-II Block under Ground Water based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000033/2024-2025 | 1198/NAD-I | 01/08/2024 | 30/09/2024 | M/S K..M. ENTERPRISE | 9.49 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000238/2022-2023 | 963 / NAD-I | 07/07/2022 | 05/09/2022 | M/S K.P. CONSTRUCTION | 75.57 | 65.61 | 86.82 | 60
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Sabdalpur Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Sabdalpur W/S Scheme under JJM (SL.NO.03) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000012/2023-2024 | 1115 / NAD-I | 27/04/2023 | 12/05/2023 | ASIT PRAMANIK | 13.01 | 12.31 | 94.62 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Dhantala Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dhantala W/S Scheme under JJM. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000099/2023-2024 | 1688/NAD-I | 12/07/2023 | 27/07/2023 | SANJIB DEY | 13.04 | 12.45 | 95.5 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Augmentation of AIRP for Ground Water Based Piped Water Supply Scheme for Dhantala (125 Cum) under Jal Jeevan Mission at Ranaghat-II Block, under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000284/2023-2024 | 2779/NAD-I | 18/12/2023 | 08/01/2024 | APURBA MANDAL | 10.62 | 10.1 | 95.11 | 100
10 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Pipeline connection from Manifold to Distribution Main (Left Part) and Rejoining with Existing Distribution Line (Right Part) under Jal Jeevan Mission (JJM) at Ranaghat-II Block under Ground Water Based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000032/2024-2025 | 1197/NAD-I | 01/08/2024 | 30/09/2024 | MANAJIT BISWAS | 9.81 | 9.46 | 96.43 | 100
11 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Sabdalpur, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no. 04) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000239/2022-2023 | 966 / NAD-I | 07/07/2022 | 26/12/2027 | M/S K.P. CONSTRUCTION | 65.89 | 46.32 | 70.29 | 70
12 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Laying dedicated pipeline to supply water for Sabdalpur and Hosenpur under Jal Jeevan Mission (JJM) at Ranaghat-II Block of Sabdalpur Ground Water Based PWSS for under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) |  |  | ORD/000021/2025-2026 | 133/NAD-I | 22/04/2025 | 21/06/2025 | MANISHIKA CONSTRUCTION | 52.42 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of SABDALPUR & DHANTALA under Ranaghat-II Block District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Constr | SM/09958 | Augmentation | Retrofitting work at Goalsalua Zone-I, Dhantala and Betna in connection with Augmentation of Ground Water based PWSS under Jaldhara/JalSwapna by retrofitting of Sabdalpur & Dhantala under Ranaghat-II Block district Nadia to accomodate FHTC, REpair of OHR construction of Boundary Wall and allied works. | Assistant Engineer-II | Junior Engineer-IV | ORD/000283/2023-2024 | 09/NAD-I | 03/01/2024 | 24/01/2024 | CHANDAN ROY | 7.89 | 0 | 0 | 100
Total | [13 empty] | 352.26 | 237.65 | 67.46