## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr | SM/09959 | Augmentation | Construction of Boundary wall, Toilet Pathway and all repair works at 2nd T W allied site and all repair works at HW site of Mamjoani under NAD I PHE Dte (Sl.no.08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000097/2022-2023 | 1963 / NAD-I | 14/10/2022 | 13/12/2022 | D.K. CONSTRUCTION | 13.16 | 11.7 | 88.91 | 0
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr | SM/09959 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Mamjoani Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 13) | Assistant Engineer-II | Junior Engineer-IV | ORD/000171/2021-2022 | 438/NAD-I | 07/03/2022 | 28/10/2023 | SHYAMAL SHIL | 88.34 | 83.23 | 94.21 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr | SM/09959 | Augmentation | Phase -II FHTC under Jaldhara/ Jal Swapna for Ramnagar at Hanskhali Block by retrofitting of Ground Water Based PWSS for Ramnagar Water Supply scheme under Nadia Arsenic Division -I, P.H.E. Dte. (Sl. no -05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000015/2022-2023 | 962 / NAD-I | 07/07/2022 | 05/09/2022 | M/S K.P. CONSTRUCTION | 81.96 | 57.6 | 70.28 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr | SM/09959 | Augmentation | Construction of Boundary wall Pathway Toilet and all repair works at 2 nd TW Site and all repair works at HW site of Ramnagar WS Scheme under NAD I PHE Dte (Sl.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000063/2022-2023 | 1595 / NAD-I | 06/09/2022 | 21/10/2022 | SANJIB DEY | 10.06 | 8.56 | 85.07 | 93
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of MAMJOANI & RAMNAGAR under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , Constr | SM/09959 | Augmentation | Work for revamping / upgradation of the hydraulic parameters at Mamjoani mouzas in reference to Mamjoani water supply scheme & Duttaphulia water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000007/2025-2026 | 76/NAD-1 | 16/04/2025 | 29/08/2026 | JOYGOPAL GUPTI | 96.49 | 0 | 0 | 57
Total | [13 empty] | 290.01 | 161.08 | 55.54