## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Betna Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Betna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 10) | Assistant Engineer-II | Junior Engineer-III | ORD/000168/2021-2022 | 436/NAD-I | 07/03/2022 | 06/04/2022 | B.M. ENTERPRISE | 25.11 | 21.53 | 85.75 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Construction of Boundary Wall Toilet Pathway and other work at Goalsalua Zone II WS Scheme within Ranaghat II Block under NAD-I PHE Dte ( Sl.no.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000093/2022-2023 | 1940 / NAD-I | 12/10/2022 | 11/12/2022 | BUDDHADEV MONDAL | 12.94 | 6.89 | 53.22 | 50
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Goalsalua Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Goalsalua Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000167/2021-2022 | 435/NAD-I | 07/03/2022 | 06/04/2022 | MANISHIKA CONSTRUCTION | 23.94 | 20.88 | 87.19 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and Pump House at Goalsalua Zone II WS Scheme in Ranaghat II Block under NAD I PHE Dte (Sl.no.07) | Assistant Engineer-II | Junior Engineer-III | ORD/000137/2022-2023 | 3036 /NAD-I | 09/11/2022 | 08/01/2023 | TAPU SAHA | 20.13 | 17.91 | 88.96 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chak Dakshinpara & Fulbari villages at Hanskhali Block by retrofitting of Ground Water based PWSS for Betna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl No. - 11) Tender No.- 224/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000175/2020-2021 | 294/NAD-I | 04/02/2021 | 21/03/2021 | K.P. CONSTRUCTION | 43.55 | 18.21 | 41.8 | 0
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Construction of Boundary Wall Toilet Pathway and other allied work at Betna WS Scheme within Hanskhali Block under NAD I PHE Dte(Sl.no.11) | Assistant Engineer-II | Junior Engineer-IV | ORD/000096/2022-2023 | 1961/ NAD-I | 12/10/2022 | 26/11/2022 | BANERJEE ENTERPRISE | 11.54 | 6.92 | 59.95 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Rejuvenation of Goalsalua (Z-i) PWSS regarding FHTC in Ranaghat II Block of Nadia Dist. |  |  | ORD/002488/2022-2023 | 926/EMD | 27/05/2022 | 27/05/2023 | SUSANTA KUMAR DAS | 12.16 | 12.16 | 100 | 0
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BETNA W/S Scheme, Block-Hanskhali , Dist. - Nadia. NIET No. 39 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/000024/2023-2024 | 1603/EMD | 26/04/2023 | 26/05/2023 | TALUKDER & CO. | 14.46 | 13.07 | 90.39 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Goalsalua Zone-I Water Supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. ( SL.NO.13) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000149/2022-2023 | 3327/NAD-I | 15/12/2022 | 29/01/2023 | M/S AKSHAY HALDER | 11.93 | 6.83 | 57.29 | 100
10 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Betna W/S Scheme under Hanskhali Block of capacity 50 cum/hr. under Nadia under augmentation of Betna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (SL.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000144/2023-2024 | 2045/NAD-I | 24/08/2023 | 22/11/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 130.98 | 8.25 | 6.3 | 65
11 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Water Supply Arrangment in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atGoalsalua (Zone-I) PWSS, Ranaghat-II Block by Augmentation of Goalsalua Zone-I &II underRanaghat-II Block & Betnaunder Hanskhali Block under Nadia Arsenic Division-I, PHE Dte (sl.10) | Assistant Engineer-I | Junior Engineer-IV | ORD/000213/2022-2023 | 205 /NAD-I | 15/02/2023 | 16/04/2023 | M/S ASOKE GHOSH & BROTHERS | 90.79 | 22.4 | 24.67 | 70
12 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Load enhancement at Betna ph-1 at Hanskhali Block, Dist.-Nadia |  |  | BILL/00543/2024-2025 | BP-27-24-25 | 24/05/2024 |  | W.B.S.E.D.C.LTD (CHITRASALI C.C.CENTER) | 1.27 | 0 | 0 | null
13 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Betna Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I, P.H.E Dte. in connection with Augmentation of Betna W/S Scheme under JJM (Sl.No.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000067/2023-2024 | 1378/NAD-I | 15/05/2023 | 09/06/2023 | TAPAS GHOSH | 12.52 | 0 | 0 | 90
14 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of GOALSALUA ZONE-I & II under Ranaghat-II Block & BETNA under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Conn | SM/09960 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR (Z-II),GOALSALUA(Z-I) & GOALSALUA(Z-II) W/S Scheme, Block- Ranaghat-II , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 1601/EMD | 26/04/2023 | 26/05/2023 | M/S DILIP MITRA | 56.44 | 17.66 | 31.28 | 100
Total | [13 empty] | 467.77 | 172.68 | 36.92