## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Chupria Zone-II Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000166/2021-2022 | 434/NAD-I | 07/03/2022 | 06/05/2022 | M/S SHIL AND CO. | 45.66 | 43.22 | 94.65 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Providing FHTC under Jaldhara / Jalswapna for Garapota P-III at Hanskhali block by retrofitting of Ground Water Based PWSS W/S Scheme under Nadia Arsenic Division -I , P.H.E. Dte. (Sl. No. 12) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000032/2022-2023 | 1512 / NAD-I | 26/08/2022 | 16/09/2022 | SAHA ENGINEERS | 43.43 | 43.43 | 99.99 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Operation & Maintenance of Distribution System and Rising Main Pipeline (CI/DI/UPVC) and Iron Elimination Plant of Different Ground Based Piped Water Supply Scheme for arsenic affected areas of Joypur, Itaberia, Chupria Z-I, Chupria Z-II, Gobindapur ( Hanskhali ) and Garapota & adjoining mouzas for the period of 1 year under Nadia Arsenic Division - I, P.H. Engineering Dte. (Sl.no. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000083/2022-2023 | 1920 / NAD-I | 30/09/2022 | 30/09/2023 | APURBA MANDAL | 28.6 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work T/W site in connectionwith Augmentation of Chupria Zone-II water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (SL.19) | Assistant Engineer-II | Junior Engineer-IV | ORD/000248/2022-2023 | 579/NAD-I | 17/03/2023 | 01/04/2023 | DIPANKAR DUTTA | 18.87 | 8.18 | 43.35 | 48
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Construction of Boundary Wall Toilet Pathway and other allied work at Chupria Zone II WS Scheme within Hanskhali Block under NAD- I PHE Dte (Sl.no.01) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000062/2022-2023 | 1594 /NAD-I | 06/09/2022 | 21/10/2022 | SUBIR KUMAR DEY | 12.65 | 12.59 | 99.46 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Repair of 450 cum capacity Over Head Reservoir ,Painting and Pump House at Chupria, Zone-II underSurface W/S Scheme in Hanskhali Block under NadiaArsenic Division - I P. H.E. Dte (Sl.no.14) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000191/2022-2023 | 154 /NAD-I | 07/02/2023 | 09/03/2023 | APURBA MANDAL | 22.4 | 22.33 | 99.69 | 45
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Garapota Bazar to H/O Chayan Biswas, Boro Chupria & Paschim Garapota to H/O Sanjiban Biswas, Boro Chupria at Hanskhali Block by retrofitting of Ground Water Based PWSS for Chupria W/S Scheme underNadia Arsenic Division-I, P.H.E. Dte. (Sl.20) | Assistant Engineer-II | Junior Engineer-IV | ORD/000267/2022-2023 | 827 / NAD-I | 31/03/2023 | 30/04/2023 | JAGADANADAPUR CO-OPT LABOUR CONTTRACT AND CONSTRUTION SOCITY LTD. | 32.85 | 20.68 | 62.96 | 0
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Retrofitting work at Kautaknagar, Ramdulalpur, under Mayurhat-I G.P. for Ground Water Based PWSS at Hanskhali Block in connection with augmenttaion of Garapota W/S Scheme under Jal Jeevna Mission (JJM) under Nadia Arsenic Division-I , PHE Dte. (Sl.no.09) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000048/2023-2024 | 1457 /NAD-I | 29/05/2023 | 19/06/2023 | TAPU SAHA | 21.99 | 21.99 | 99.99 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work T/W site in connection with Augmentation of Garapota water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. ( sl.no.12) | Assistant Engineer-II | Junior Engineer-IV | ORD/000249/2022-2023 | 580/NAD-I | 17/03/2023 | 07/04/2023 | ONKAR ENTERPRISE | 19.03 | 18.76 | 98.59 | 100
10 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GARAPOTA,BHAYNA(Z-I), BHAYNA(Z-II) & MAMJOANI W/S Scheme, Block-HANSKHALI , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000025/2023-2024 | 1604/EMD | 26/04/2023 | 26/05/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 61.43 | 52.83 | 86 | 80
11 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Repair of 550 cum capacity Over Head Reservoir, Painting of Pump House in connection with Augmentation of Garapota W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.23) | Assistant Engineer-II | Junior Engineer-IV | ORD/000097/2023-2024 | 892/NAD-I | 04/04/2023 | 04/05/2023 | S B CONSTRUCTION | 26.31 | 23.54 | 89.45 | 75
12 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Shifting of LT OH line by erection of 2nos PCC pole 8meter long at Garapota (Ph-1) at Hanskhali block, Dist.-Nadia |  |  | BILL/00334/2024-2025 | BP-20-24-25 | 21/05/2024 | 21/05/2024 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 0.41 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Conversion of IEP to AIRP (Pressure Type) at Garapota W/S Scheme under Hanskhali Block of capacity 120 cum/hr. under augmentation of Garapota W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000133/2023-2024 | 1901/NAD-I | 14/08/2023 | 28/03/2025 | HARBAUER INDIA PRIVATE LIMITED | 166.14 | 42.92 | 25.83 | 56
14 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Chupria Zone-II Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Chupria Zone-II W/S Scheme under JJM (SL.NO.13) | Assistant Engineer-II | Junior Engineer-IV | ORD/000013/2023-2024 | 1117 / NAD-I | 27/04/2023 | 11/04/2025 | MONDAL ENTERPRISE | 12.96 | 0 | 0 | 100
15 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Garapota Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Garapota W/S Scheme under JJM (Sl.no 08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000082/2023-2024 | 1072/NAD-I | 24/04/2023 | 01/05/2025 | SWAPAN KUMAR BISWAS | 12 | 0 | 0 | 100
16 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of CHUPRIA ZONE-II & GARAPOTA Under Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Construction AIRP , | SM/09961 | Augmentation | Shifting of existing 11KV HT pole by erecting DTR DP & PHE DTR from its current position at Garapota ph-1, Ref no.- E-340958 |  |  | BILL/00298/2025-2026 |  | 19/05/2025 | 19/05/2025 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 2.88 | 0 | 0 | 0
Total | [13 empty] | 527.61 | 310.46 | 58.84