## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha | SM/09962 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-VIII (Barberia) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000170/2021-2022 | 430/NAD-I | 07/03/2022 | 06/05/2022 | SANDIP BISWAS | 85.12 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha | SM/09962 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X (Shimurali) Part III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000162/2021-2022 | 431/NAD-I | 07/03/2022 | 06/05/2022 | CHAKRABORTTI ENTERPRISE | 67.64 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha | SM/09962 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Chanduria) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-II | Junior Engineer-III | ORD/000164/2021-2022 | 432/NAD-I | 07/03/2022 | 06/05/2022 | SANJOY BAKSHI | 78.61 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha | SM/09962 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000119/2021-2022 | 12/NAD-I | 05/01/2022 | 05/04/2022 | UMWELT ENGINEER PVT. LTD. | 299.45 | 0 | 0 | 98
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha | SM/09962 | Augmentation | Repair of 950 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Chanduria Zone-XI under Surface W/S Scheme of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte.( Sl.no . 04) | Assistant Engineer-I | Junior Engineer-I | ORD/000056/2022-2023 | 1636/NAD-I | 06/09/2022 | 21/10/2022 | M/S R.K. ENTERPRISE | 37.67 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha | SM/09962 | Augmentation | Retrofitting work of Chanduria Zone XI at Priyanagar New Kautukpur Kautukpur Jibannagar village under Chakdah Block of PWSS for Chakdah Surface water supply scheme under NAD I PHE Dte ( Sl.no. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000095/2022-2023 | 1960 / NAD-I | 12/10/2022 | 11/12/2022 | MADE AND TRADE CO. | 15.76 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VIII (BARBERIA), Zone-X (SHIMURALI) & Zone-XI (CHANDURIA) at chakdaha | SM/09962 | Augmentation | Retrofitting work of Barberia, Zone-VIII, at Chakdah Block of PWSS for Chakdah Surface Water Supply Scheme under Nadia arsenic Division-I, P.H.E. Dte. (Sl No.-01) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-III | ORD/000169/2022-2023 | 87/ AE-II/ NAD-I | 30/06/2022 | 30/07/2022 | UMWELT ENGINEER PVT. LTD. | 3.89 | 0 | 0 | 100
Total | [13 empty] | 588.13 | 0 | 0