## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Laying of UPVC pipeline at different location of Zone-II (Hapania) under Nagarukhra-I & II G.P. under 'surface water based piped water supply scheme of HARINGHATA & CHAKDAHA under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000017/2022-2023 | 88/AE-I/NAD-I | 28/04/2022 | 13/05/2022 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 0 | 90
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Laying of UPVC pipeline at different location of Jalkar Bhomra (Zone-III) Madanpur (Zone-XII) Birohi (Zone-XI) under Kastodanga-I & II Madanpur-I & II Birohi-I G.P. respectively under 'surface water based piped water supply scheme of HARINGHATA & CHAKDAHA under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000018/2022-2023 | 89/AE-I/NAD-I | 28/04/2022 | 13/05/2022 | AVINABA ENGINEERING CONCERN | 4.82 | 0 | 0 | 85
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Phase-III FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX Ghetugachi, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl. no. 02) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000012/2022-2023 | 964/NAD-I | 07/07/2022 | 05/09/2022 | B.S. ENTERPRISE | 65.97 | 52.76 | 79.98 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-V, (Purba Bishnupur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000178/2021-2022 | 515/NAD-I | 28/03/2022 | 27/05/2022 | APURBA MANDAL | 156.91 | 155.28 | 98.96 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Repair of 800 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Purba Bishnupur Zone-V under Chakdah Surface WS Scheme in Chakdah Block under NAD-I PHE Dte (Sl.no.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000059/2022-2023 | 1670/ NAD-I | 07/09/2022 | 06/11/2022 | TAPU SAHA | 33.13 | 29.11 | 87.87 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Repair of 350 cum capacity Over Head Reservoir Two Nos Painting and repairing of HW Boundary Wall, Pump House at Ghetugachi Zone IX under urface WS Scheme of Chakdah Part under NAD I PHE Dte (Sl.no.12) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000102/2022-2023 | 1985 / NAD-I | 18/10/2022 | 02/12/2022 | U TURN CONSTRUCTION | 22.32 | 20.02 | 89.69 | 100
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Retrofitting work at Tangra & Bagdob for augmentation of Surface water based PWSS for providing FHTC at Purba Bishnupur ( Zone V) of Surfac water based piped water supply scheme for Chakdah ( Part ) under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (SL.No.11) | Assistant Engineer-II | Junior Engineer-IV | ORD/000076/2023-2024 | 1400/NAD-I | 16/05/2023 | 10/06/2023 | CHANDAN ROY | 47.15 | 43.79 | 92.87 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Retrofitting work along Simurali-Kalibazar Road of Ghetugachi (Zone-IX) Water Supply Scheme under Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000126/2023-2024 | 1839/NAD-I | 07/08/2023 | 22/08/2023 | PURNIMA ELECTRICS & DECORATORS | 9.19 | 7.72 | 83.97 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-V (Purba Bishnupur), & Zone-IX (Ghetugachhi), at chakdaha Block, by retr | SM/09963 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 1781/NAD-I | 22/09/2022 | 22/09/2022 | Resource Division | 20.28 | 0 | 0 | 0
Total | [13 empty] | 364.61 | 308.68 | 84.66