## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA Darappur, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl.No. 03) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000013/2022-2023 | 965/NAD-I | 07/07/2022 | 05/09/2022 | M/S K.P. CONSTRUCTION | 78.62 | 0 | 0 | 40
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VI (BALIA) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000163/2021-2022 | 429/NAD-I | 07/03/2022 | 06/05/2022 | BIDYUT KUMAR | 87.82 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House Darrappur Z-VIA under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no. 06) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000038/2022-2023 | 1531/ NAD-I | 30/08/2022 | 14/10/2022 | MAA LAXMI ENTERPRISE | 17.21 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Ballavpur Zone- VII under Surface (Sl.no.07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000098/2022-2023 | 1964 / NAD-I | 14/10/2022 | 28/11/2022 | D.C. RAKSHIT & SONS INDIA PVT LTD | 29.25 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 1781/NAD-I | 22/09/2022 | 22/09/2022 | Resource Division | 14.93 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VII, (Ballavpur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000177/2021-2022 | 514/NAD-I | 28/03/2022 | 27/05/2022 | MANGES INDUSTRIAL CORPORATION | 125 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Repair of 550 cum capacity Over Head Reservoir, Boundary Wall, Switch Room and other allied works at Balia (Zone-VI) under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division ? I, P. H..E. Dte (SL NO. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000066/2023-2024 | 1367/NAD-I | 12/05/2023 | 11/06/2023 | M/S COSMOPOLITAN TRADERS | 23.55 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Providing FHTC (Functional Household Tap Connection) Repair of OHR & allied works under Jaldhara / Jal Swapna Zone-VI (BALIA), Zone-VIA (DARRPPUR) & Zone-VII (BALLAVPUR), at chakdaha Bloc | SM/09964 | Augmentation | Retrofitting work at Lakshmipur and Srinagar under Ballavpur W/S Scheme in connection with augmentation of Ballavpur W/S Scheme under Chakdah (Part) W/S Scheme under JJM under NadiaArsenic Division-I, PHE Dte. (sl.no.18) | Assistant Engineer-II | Junior Engineer-I | ORD/000200/2023-2024 | 2243/NAD-I | 21/09/2023 | 06/10/2023 | MANGES INDUSTRIAL CORPORATION | 9.54 | 0 | 0 | 100
Total | [13 empty] | 385.92 | 0 | 0