## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Shifting of UPVC distribution main pipe line from Palagacha more to WTP of Palagacha (Zone-I) W/S Scheme under Chakdah Surface W/S Scheme under Nadia Arsenic Division-I PHE Dte.(sl.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000127/2022-2023 | 1424 / NAD-I | 12/08/2022 | 11/09/2022 | G.B. CONSTRUCTION | 29.6 | 24.88 | 84.05 | 0
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Water Supply Arrangement in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atMosra (Zone-III) Kalyani Block under Palagachha (Zone-I) & Mosra (Zone-III) Dist.-Nadia of Surface Water Based PWSS for Chakdah (Part) Surface Water Based Water Supply Scheme of Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (sl.no. 07) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000215/2022-2023 | 242 / NAD-I | 17/02/2023 | 04/03/2023 | M/S S.K ENTERPRISE | 10.79 | 9.26 | 85.81 | 60
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Retrofitting work at DD Brick Field at Palagacha in connection with augmentation of Zone-I, Palagacha W/S Scheme under Surface Water Based PWSS for Chakdah (Part) under Jal Jeevan Mission under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte.(sl.03) | Assistant Engineer-I | Junior Engineer-II | ORD/000275/2022-2023 | 170//AE-II/NAD-I | 27/03/2023 | 17/04/2023 | K K MARKETING | 4.48 | 4.28 | 95.65 | 0
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-I, (Palagachha), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000179/2021-2022 | 516/NAD-I | 28/03/2022 | 27/05/2022 | SHYAMAL SHIL | 134.14 | 134.07 | 99.95 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Masra (Zone- III) under Chakdah Surface WS Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.09) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000136/2022-2023 | 1969 / NAD-I | 14/10/2022 | 13/12/2022 | RAM KRISHNA CHAKRABORTY | 26.49 | 23.33 | 88.08 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Masra (Zone-III), (Part-II) Water Supply Scheme under Chakdah (Part) Surface Water Based W/S Scheme under Nadia Arsenic Division-I, PHE Dte. Sl. No.- 11 | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000151/2022-2023 | 3329/NAD-I | 15/12/2022 | 29/01/2023 | KESHOB ENTERPRISE | 28.27 | 27.95 | 98.85 | 0
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Palagachha Zone-I Chakdah Block Palagachha (Zone-I) & Mosra (Zone-III) at Chakdah Block, Dist- Nadia of Surface Water Based PWSS for Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000177/2022-2023 | 33/NAD-I | 17/01/2023 | 01/02/2023 | SUNIL KUMAR DATTA | 11.95 | 10.98 | 91.89 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Supply and installation of Butterfly Valve at Back Wash OHR at Palagachha under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-IV | ORD/000045/2023-2024 | 246/AE-II/NAD-I | 18/05/2023 | 25/05/2023 | SATYABRATA CHAKRABORTY | 2.76 | 2.65 | 95.79 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Retrofitting work at RanjanPally, Lalpur and Singher Bagan under Palagacha W/S Scheme under JJM within Chakdah Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000160/2023-2024 | 2118/NAD-I | 04/09/2023 | 19/09/2023 | MANAJIT BISWAS | 13.58 | 13.07 | 96.25 | 100
10 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Retrofitting works at Balir math and Palagachha (Zone-I) W/S Scheme under Surface Water Based PWSS for Chakdah (Part) water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 09) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-IV | ORD/000126/2022-2023 | 3042/NAD-I | 09/11/2022 | 08/01/2023 | BUDDHADEV MONDAL | 9.28 | 9.27 | 99.97 | 100
11 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Repair of 350 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Palagacha Zone-I under Chakdah Surface W/S Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000064/2022-2023 | 1597/NAD-I | 06/09/2022 | 21/10/2022 | M/S PRADIP KUMAR PAL | 12.72 | 12.31 | 96.8 | 100
12 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Phase-III FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III (Masra), at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000152/2022-2023 | 3446/NAD-I | 21/12/2022 | 20/01/2023 | SUMIT GHOSH | 39.83 | 34.06 | 85.5 | 100
13 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Retrofitting work for clear water rising main & distribution main at Palagachha Zone-I W/S Scheme in connection with Augmentation of Palagachha (Zone-I) & Masra (Zone-III) under JJM under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 12)" | Assistant Engineer-I | Junior Engineer-II,Junior Engineer-IV | ORD/000077/2023-2024 | 1411/NAD-I | 18/05/2023 | 08/06/2023 | THE TOWER CONSTRUCTION | 36.38 | 30.5 | 83.83 | 75
14 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Retrofitting work at Node Point 180 to 180 at Lalpur of Palagacha (Zone-I) W/S Scheme under Chakdah Surface W/S Scheme at Chakdah Block under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte | Assistant Engineer-II | Junior Engineer-IV | ORD/000148/2023-2024 | 376/AE-II/NAD-I | 29/08/2023 | 05/09/2023 | M/S K..M. ENTERPRISE | 4.71 | 4.29 | 90.96 | 100
15 | NADIA |  | Nadia Arsenic Division I | Augmentation of Surface Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of PALAGACHHA (ZONE-I) & MOSRA (ZONE-III) at chakdaha Block,District-Nadia of Surface Water based PWSS for Chakdah (Part) for FHTC (Functional Househ | SM/09965 | Augmentation | Retrofittng work at Mahanala due to construction of N.H.-34 road under Palagacha (Zone-I ) within Chakdah Surface W/S Scheme under JJM under Nadia Arsenic Division-I ,PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000154/2023-2024 | 2113/NAD-I | 01/09/2023 | 16/09/2023 | K K MARKETING | 6.82 | 4.77 | 69.9 | 100
Total | [13 empty] | 371.79 | 345.65 | 92.97