## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Joypur Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000165/2021-2022 | 433/NAD-I | 07/03/2022 | 06/05/2022 | M/S GHOSH CONSTRUCTION | 60.4 | 56.94 | 94.27 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Itaberia PWSS Hanskhali Block (Part-I) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000157/2022-2023 | 3489/NAD-I | 02/01/2023 | 23/01/2023 | BUDDHADEV MONDAL | 19.22 | 18.72 | 97.42 | 99
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Repair of 450 cum capacity Over Head Reservoir, Painting and Pump House at Gobindapur W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl. No. 10) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000039/2022-2023 | 1589/NAD-I | 05/09/2022 | 20/10/2022 | APURBA MANDAL | 14.41 | 14.38 | 99.73 | 40
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Construction of Boundary Wall, Toilet, pathway and other allied work at Joypur W/S scheme within Hanskhali Block under Nadia Arsenic Division -I, P.H.E.Dte.( Sl.no.01) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000052/2022-2023 | 1590 / NAD-I | 06/09/2022 | 21/10/2022 | M/S DREAM INFRASTRUCTURE | 12.41 | 12.35 | 99.5 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Construction of Boundary wall, Toilet, Pathway and all repair works at Itaberia W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (sl.no.03) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000055/2022-2023 | 1638 / NAD-I | 06/09/2022 | 21/10/2022 | APURBA MANDAL | 12.04 | 11.99 | 99.6 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at ITABERIA W/S Scheme & Betna W/S Scheme at Hanskhali Block under Nadia Arsenic Division-I , P.H.E.Dte. (Sl.no. 10) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000043/2022-2023 | 1583/NAD-I | 06/09/2022 | 21/10/2022 | SATYABRATA CHAKRABORTY | 28.26 | 28.19 | 99.73 | 100
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Itaberia WS Scheme in Hanskhali Block under NAD I PHE Dte (Sl.no.12) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000109/2022-2023 | 2058 / NAD-I | 21/10/2022 | 05/12/2022 | M/S D.C. RAKSHIT & COMPANY | 19.77 | 19.63 | 99.28 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Repair of 350 cum capacity Over Head Reservoir, Painting of Boundary Wall of Head Work Site, Pump House and AIRP at Joypur W/S Scheme in Hanskhali Block under Nadia Arsenic Division - I P. H.E. Dte (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000074/2023-2024 | 1258/NAD-I | 04/05/2023 | 19/05/2023 | GHOSH CONSTRUCTION | 21.34 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Construction of Boundary wall, Toilet , Pathway and other allied work at Gobindapur (Hanskhali) W/S Scheme within Hanskhali Block under Nadia Arsenic Division -I, P.H.E.Dte.(Sl.no. 02) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000048/2022-2023 | 1588 / NAD-I | 06/09/2022 | 21/10/2022 | GOPAL KIRTYANIYA | 11.82 | 11.76 | 99.48 | 100
10 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Construction of AIRP capacity (104m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-I under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000025/2024-2025 | 1118/NAD-I | 19/07/2024 | 15/01/2025 | HARBAUER INDIA PRIVATE LIMITED | 265.04 | 0 | 0 | 0
11 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Joypur PWSS Hanskhali Block (Part-III) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000162/2022-2023 | 3514/NAD-I | 09/01/2023 | 30/01/2023 | SUBIR KUMAR DEY | 19.99 | 0 | 0 | 100
12 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Gobindapur PWSS Hanskhali Block (Part-II) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia under Nadia Arsenic Division-I, PHE Dte (sl.no.04) | Assistant Engineer-II | Junior Engineer-I | ORD/000161/2022-2023 | 3513/NAD-I | 09/01/2023 | 30/01/2023 | M/S DIPAK ENTERPRISE | 19.75 | 0 | 0 | 100
13 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Itaberia Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Itaberia W/S Scheme under JJM (sl.no.11) | Assistant Engineer-II | Junior Engineer-IV | ORD/000016/2023-2024 | 1122 /NAD-I | 27/04/2023 | 12/05/2023 | B.S. ENTERPRISE | 13.04 | 0 | 0 | 100
14 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of ITABERIA, GOBINDAPUR & JOYPUR at Hanskhali Block, District-Nadia to accommodate FHTC (Functional Household Tap Connection), Repair of OHR, Cons | SM/09966 | Augmentation | 'Construction and installation of MANIFOLD and allied works at OHR site under Gobindapur Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E [he. in connection with Augmentation of Gobindapur W/S Scheme under JIM (SL No. 10)". | Assistant Engineer-II | Junior Engineer-IV | ORD/000068/2023-2024 | 1071/NAD-I | 24/04/2023 | 26/04/2025 | APURBA MANDAL | 13.03 | 0 | 0 | 100
Total | [13 empty] | 530.52 | 173.96 | 32.79