## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Repair of 350 cum capacity Over Head Reservoir and Painting of all structures with repair works & other allied works at Dubli Zone -II W/S Scheme within Ranaghat -Ii Block under Nadia Arsenic Division -I, P.H.E.DTE. (Sl.no. 26) | Assistant Engineer-II | Junior Engineer-III | ORD/000047/2022-2023 | 1587 / NAD-I | 06/09/2022 | 21/10/2022 | SATYABRATA CHAKRABORTY | 17.14 | 0 | 0 | 0
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Retrofitting work from Ukhilnara More towards Payradanga Station under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl.no. 03) | Assistant Engineer-I | Junior Engineer-I | ORD/000224/2022-2023 | 107/ AE-II/NAD-I | 02/03/2023 | 17/03/2023 | GANGULY ENTERPRISE | 2.64 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Construction of M.S. Manifold of 1000mm thickness for improvement of Water Supply at Head Work Site under Ukhilnara Zone-I Ground Water Based Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation of Ukhilnara Zone-I W/S Scheme underJJM (sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000017/2023-2024 | 1153 /NAD-I | 28/04/2023 | 13/05/2023 | GANGULY ENTERPRISE | 13.05 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Repair of 100 cum capacity and other allied works at Ukhilnara Zone-II W/S Scheme in Ranaghat -I Block under Nadia Arsenic Division -I , P.H.E.Dte. (Sl no. 17) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000026/2022-2023 | 1320 / NAD -I | 04/08/2022 | 18/09/2022 | INVENT ENGINEER'S CO - OPERATIVE SOCIETY LTD. | 11.32 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | CONSTRUCTION OF BOUNDARY WALL,TOILET ,PATHWAY AND ALL REPAIR WORKS AT 2nd T/W AND OTHER ALLIE WORKS AT DUBLI Z-II W/S SCHEME AT RANAGHAT -II BLOCK , UNDER NADIA ARSENIC DIVISION -I , P.H.E.DTE. ( SL NO.21) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000035/2022-2023 | 1515 / NAD-I | 26/08/2022 | 10/10/2022 | DAS CONSTRUCTION | 16.36 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Phase -II FHTC under Jaldhara/ Jal Swapna for Dubli Z-I & II at Ranaghat -II Block by retrofitting of Ground Water Based PWSS for Dubli Water Supply scheme under Nadia Arsenic Division -I, P.H.E. Dte. (Sl. no -08) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000010/2022-2023 | 960 / NAD-I | 07/07/2022 | 05/09/2022 | BIPLAB GUHA | 55.81 | 0 | 0 | 85
7 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Construction of Boundary Wall, Toilet , Pathway and all repair works at nd T/W site and other allied works at Ukhilnara Z-I W/S Scheme at Ranaghat -I Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl. No. 23) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000034/2022-2023 | 1514 / NAD-I | 26/08/2022 | 10/10/2022 | NISHITH BANERJEE | 22.91 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Repairs and Renovation work of Arsenic cum Iron Removal Plant having Capacity 16 m3/hr including Civil Structures of Ukhilnara Zone-II W/S Sch. within Ranaghat -I Block under Nadia Arsenic Division -I , P.H.E. Dte. (SL.No. 22) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000033/2022-2023 | 1513 / NAD-I | 26/08/2022 | 10/10/2022 | SUNIL KUMAR DATTA | 7.1 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Repair of 450 cum capacity over head reservoir and painting of all structures with repair Works & other allied works at Dubli Z-I W/S scheme in Ranaghat -II Block under Nadia Arsenic Division -I (Sl.no. 24) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000044/2022-2023 | 1584 / NAD-I | 06/09/2022 | 21/10/2022 | SATYABRATA CHAKRABORTY | 15.84 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Construction of Boundary Wall Toilet Pathway and other allied works at 2nd and 3rd TW site of Dubli Zone I WS Scheme within Ranaghat II Block under NADI PHE Dte (sl.no.01) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000150/2022-2023 | 3328/NAD-I | 15/12/2022 | 29/01/2023 | B.M. ENTERPRISE | 20.53 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Repair of 180 cum capacity Over Head Reservoir and painting of all structures with repair works and other allied works at Ukhilnara Zone-I W/S Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.06) | Assistant Engineer-I | Junior Engineer-I | ORD/000068/2022-2023 | 1442/NAD-I | 17/09/2022 | 01/11/2022 | MONDAL ENTERPRISE | 14.98 | 0 | 0 | 100
12 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Retrofitting in Uzirpukuria North at Dubli Zone-I W/S Scheme under Ground Water Based PWSS for arsenic affected areas of Dubli W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000200/2022-2023 | 28/AE-II/NAD-I | 10/02/2023 | 25/02/2023 | BUDDHADEV MONDAL | 4.8 | 0 | 0 | 100
13 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Shifting of pipeline From Headwork site to Ukhilnara More due to widening of PWD Road under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte (sl.01) | Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000223/2022-2023 | 106/AE-II/ NAD-I | 02/03/2023 | 17/03/2023 | GANGULY ENTERPRISE | 1.86 | 0 | 0 | 50
14 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Retrofitting work at Mistripara under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte (sl.02) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000274/2022-2023 | 169 / AE-II/NAD-I | 27/03/2023 | 17/04/2023 | MALI CONSTRUCTION | 2.79 | 0 | 0 | 100
15 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Improvement of AIRP for Dubli Zone-I (105 cum/hr.) W/S Scheme in connection with Augmentation of AIRP for Ground Water Based Piped Water Supply Scheme for Dubli Zone-I, under Jal Jeevan Mission at Ranaghat-II Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.14) | Assistant Engineer-II | Junior Engineer-IV | ORD/000188/2023-2024 | 2151/NAD-I | 08/09/2023 | 29/09/2023 | SATYABRATA CHAKRABORTY | 63.28 | 0 | 0 | 100
16 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Laying of UPVC Pipeline under JJM for Ukhilnara Zone-II at Payradanga G.P. at Ranaghat-I Block of Ground Water Based PWSS for Ukhilnara Zone-II W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000270/2023-2024 | 2752/NAD-I | 11/12/2023 | 21/10/2024 | GANGULY ENTERPRISE | 9.32 | 0 | 0 | 90
17 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Augmentation & Retrofitting work under Jal Jeevan Mission (JJM) for UKILNARA ZONE-I at Ranaghat-I Block of Ground Water based PWSS for Ukilnara Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000167/2024-2025 | 1897/NAD-I | 18/11/2024 | 14/09/2025 | GANGULY ENTERPRISE | 29.52 | 0 | 0 | 0
18 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme under Jaldhara / Jal Swapna by retrofitting of DUBLI ZONE-I & DUBLI ZONE-II of Ranaghat-II Block, & UKHILNARA ZONE-I & UKHILNARA ZONE-II of Ranaghat-I Block, District-Nadia to accommodate FHT | SM/09967 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Ukhilnara Zone-II Ground Based Water Supply Scheme under Ranaghat- I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Ukhilnara Zone-II W/S Scheme under JJM (sl.03) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000019/2023-2024 | 1156 /NAD-I | 28/04/2023 | 02/05/2025 | K K MARKETING | 13.04 | 0 | 0 | 100
Total | [13 empty] | 322.28 | 0 | 0