## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-III (Jalkar Bhomra) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte ( Sl No. 08) | Assistant Engineer-I | Junior Engineer-I | ORD/000157/2021-2022 | 424/NAD-I | 07/03/2022 | 06/05/2022 | MONDAL ENTERPRISE | 90.02 | 84.48 | 93.85 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Laying of UPVC Pipeline at different locations of Jalkar Bhomra(Zone-III),Madanpur(Zone-XII) and Birohi(Zone-XI) under Kastodanga-I & II, Madanpur-I & II and Birohi-I G.P. respectively under Haringhata & Chakdah (Part) Surface Water Supply scheme Under Nadia Arsenic Division-I,PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000077/2022-2023 | 89/ AE-I/NAD-I | 28/04/2022 | 13/05/2022 | AVINABA ENGINEERING CONCERN | 4.82 | 4.82 | 100 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-IV (Uttar Duttapara) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl. NO. 09) | Assistant Engineer-I | Junior Engineer-I | ORD/000158/2021-2022 | 425/NAD-I | 07/03/2022 | 06/05/2022 | SARKAR AGENCY | 91.65 | 91.25 | 99.56 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Augmentation work for Balance Portion of Zone-XI (Birohi) and Zone-III (Jalkar Bhomra) in connection with Augmentation of Zone-III (Jalkar Bhomra) Part-III at Haringhata Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.1) | Assistant Engineer-I | Junior Engineer-II | ORD/000039/2023-2024 | 237 /AE-I/NAD-I | 18/05/2023 | 25/05/2023 | BUDDHADEV MONDAL | 4.81 | 4.81 | 99.97 | 0
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Shifting and Laying of D.I. (K9) Pipes at Kalyani More along (NH-34) in connection with Augmenation of Zone-IV (Uttar Duttapara) Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000040/2023-2024 | 238 /AE-I/NAD-I | 18/05/2023 | 25/05/2023 | BUDDHADEV MONDAL | 4.56 | 4.56 | 99.93 | 0
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Augmentation Work of Zone-IV (Uttar Duttapara) Part-III under JJM in connection with Surface Water based PWSS for Haringhata and Chakdah (Part) in Haringhata Block under Nadia Arsenic Division-I, P.H.E. Dte(sl.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000029/2023-2024 | 1253 / NAD-I | 04/05/2023 | 03/06/2023 | CHOWDHURY & CO. | 95.64 | 95.19 | 99.52 | 0
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Repair of 900 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Jalkar Bhomra, Zone-III under Surface W/S Scheme of Haringhata-Chakdah Part under NAD I PHE Dte (Sl.no.09) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000071/2022-2023 | 1702 / NAD-I | 09/09/2022 | 08/11/2022 | GHOSH CONSTRUCTION | 33.26 | 30.48 | 91.63 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Retrofiting of work in Kastodanga -II, G.P. at Jalkar Bhomra (Zone-III) under Surface Water based PWSS for arsenic affected areas of Haringhata and Chakdah (Part) Block under Nadia Arsenic Division -I P.H.E. Dte. (Sl No.-06) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-II | ORD/000170/2022-2023 | 166 /AE-I/ NAD-I | 04/07/2022 | 19/07/2022 | MONDAL ENTERPRISE | 4.84 | 4.84 | 100 | 100
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Repair of 600 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Uttar Duttapara, Zone-IV under Surface W/S Scheme of Haringhata-Chakdah (Part) under JJM under Nadia Arsenic Division - I P. H.E. Dte (sl.21) | Assistant Engineer-I | Junior Engineer-I | ORD/000266/2022-2023 | 830/NAD-I | 31/03/2023 | 21/04/2023 | MS MAA BHABANI ENTERPRISE | 24.42 | 24.38 | 99.83 | 100
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra) and Zone- IV, (Uttar Duttapara), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Wate | SM/09969 | Augmentation | Providing FHTC (Functional Household Tap Connection) and Recoonection at Ayeshpur,Sonakhali at Birohi-I G.P & Dakshin Rajapur at Birohi-II G.P under Jal Jeevan Mission (JJM) for Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Birohi under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000203/2023-2024 | 463/AE-I/NAD-I | 05/10/2023 | 04/11/2023 | MANAJIT BISWAS | 3.99 | 0 | 0 | 100
Total | [13 empty] | 358.02 | 344.8 | 96.31