## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. | SM/09971 | Augmentation | Repair of 450 cum capacity Over Head Reservoir ,Painting and Pump House at Chupria, Zone-I under Surface W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, P. H.E. Dte (Sl. No.16) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000190/2022-2023 | 153/NAD-I | 07/02/2023 | 09/03/2023 | PAPAN ROY | 13.66 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. | SM/09971 | Augmentation | Construction of Boundary wall, Toilet, Pathway and other allied work at H/W Site (Length-135.0 m) and 2nd T/W Site (Length-55.0m) in Chupria Zone-I water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. (SL.NO.17) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000183/2022-2023 | 104 / NAD-I | 31/01/2023 | 17/03/2023 | GOPAL KIRTYANIA | 24.03 | 0 | 0 | 40
3 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. | SM/09971 | Augmentation | Retrofitting work at Chupria Zone-I under Jal Jeevan Mission (JJM) for Chupria Zone-I W/S Scheme at Hanskhali Block in connection with augmentation of Ground Water based W/S Scheme for Chupria Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl.no.19) | Assistant Engineer-II | Junior Engineer-I | ORD/000184/2023-2024 | 2155/NAD-I | 08/09/2023 | 29/09/2023 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 71.93 | 0 | 0 | 80
4 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. | SM/09971 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Chupria Zone-I Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Chupria Zone-I W/S Scheme under JJM (SL.NO.12) | Assistant Engineer-II | Junior Engineer-IV | ORD/000015/2023-2024 | 1116 / NAD-I | 27/04/2023 | 12/05/2023 | SAHA CONSTRUCTION &CO | 13.05 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. | SM/09971 | Augmentation | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Chupria (Zone -I) Part -I at Hanskhali Block by retrofitting of Grond Water based PWSS for CHUPRIA Water Supply Sceme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.01) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000066/2022-2023 | 1673 / NAD-I | 07/09/2022 | 28/02/2024 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 565.67 | 0 | 0 | 85
6 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for CHUPRIA ZONE-I, BLOCK- Hanskhali, Dist-Nadia. | SM/09971 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Chupria Zone-I ii)Garapota iii)Itaberia iv)Muragachha Zone-I v)Muragachha Zone-II vi)Zone-I (Palagachha) vii)Zone-II (joykrishnapur) | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000007/2023-2024 | 169/AE-I/NAD-I | 12/04/2023 | 08/10/2026 | TECH VISION | 4.84 | 0 | 0 | 100
Total | [13 empty] | 693.18 | 0 | 0