## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Beharia, Nabla, Goalpur Zone-I and Goalpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla, Goalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-I | Junior Engineer-II | ORD/000154/2021-2022 | 421/NAD-I | 07/03/2022 | 06/05/2022 | CHOWDHURY & CO. | 95.27 | 90.4 | 94.89 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Nabla, Part-IV at Santipur block by retrofitting/augmentation of Ground Water Based PWSS for Nabla W/S scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 18) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000025/2022-2023 | 1319/NAD-I | 04/08/2022 | 03/09/2022 | CHOWDHURY & CO. | 55.7 | 55.69 | 99.98 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Beharia WS Scheme Santipur Block under NAD PHE Dte (Sl.no.01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000076/2022-2023 | 1831 / NAD-I | 27/09/2022 | 11/11/2022 | PALCON | 24.15 | 24.1 | 99.82 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Boundary wall , Toilet, Pathway and other allied work at Goalpur Z-II WAter Supply scheme within Santipur block under Nadia Arsenic Division -I , P.H.E.Dte. ( Sl.no. 01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000080/2022-2023 | 219 / AE-I/NAD-I | 02/09/2022 | 02/10/2022 | BUDDHADEB MONDAL | 0.97 | 0.97 | 99.88 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Repair of 136 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House and AIRP at Nabla W/S Scheme Santipur Block under NAD- I PHE Dte (Sl.no.03) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000075/2022-2023 | 1799 /NAD-I | 26/09/2022 | 10/11/2022 | M/S S & P CONSTRUCTION | 15.29 | 15.24 | 99.69 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Repair of 100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Goalpur, Zone-I W/S Scheme of Santipur Block under NAD- I, PHE Dte ( Sl.no.18) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000067/2022-2023 | 1725 / NAD-I | 13/09/2022 | 28/10/2022 | MONDAL ENTERPRISE | 11.12 | 11.09 | 99.65 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Nabla W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no. 15) | Assistant Engineer-I | Junior Engineer-I | ORD/000140/2022-2023 | 3093/NAD-I | 21/11/2022 | 05/01/2023 | G S CONSTRUCTION AND CO. | 14.24 | 14.12 | 99.18 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Boundary wall Toilet Pathway and other allied work at Goalpur Zone I WS Scheme within Santipur Block under Nadia Arsenic Division-I, PHE Dte ( Sl.No.02) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000074/2022-2023 | 1798 / NAD-I | 26/09/2022 | 10/11/2022 | N.H. ENTERPRISE | 14.18 | 14.08 | 99.28 | 100
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House and AIRP at Goalpur Zone-II under Nadia Arsenic Division -I, P.H.E.DTE. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000142/2022-2023 | 3157 / NAD-I | 25/11/2022 | 24/01/2023 | DAS CONSTRUCTION | 11.08 | 11.04 | 99.67 | 100
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Boundary Wall, Toilet, Pathway and other allied work at Beharia W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no.16) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000119/2022-2023 | 2010 / NAD-I | 19/10/2022 | 03/12/2022 | S S CONSUTANCYAND CONSTRUCTION | 13.08 | 13.05 | 99.76 | 100
11 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Augmentation work of laying of UPVC and M.S. pipeline and other allied works at Goalpur mouza under Jal Jeevan Mission (JJM) under Goalpur Zone-II, Part-III at Santipur Block under Ground Water Based PWSS for Goalpur Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. (sl.17) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000240/2022-2023 | 536 / NAD-I | 13/03/2023 | 03/04/2023 | CHOWDHURY & CO. | 14.94 | 14.94 | 100 | 30
12 | NADIA |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Providing Drilling Crew and other allied works for construction of TW (250mm x 150mm x 300mtr. depth) by utilising Departmental Machineries for Goalpur WS Scheme (Z-II), Santipur-I Block under Nadia District, CDD,PHE Dte. | Driller In Charge | Junior Engineer | ORD/000331/2022-2023 | 1452/CDD | 30/11/2022 | 30/12/2022 | M/S SAIKAT ENTERPRISE | 15.55 | 10.86 | 69.83 | 0
13 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | Assistant Engineer-I | Junior Engineer-II | ORD/000046/2023-2024 | 1364/NAD-I | 12/05/2023 | 27/05/2023 | DEBASISH DEY | 12.2 | 5.49 | 45.03 | 100
14 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Malipota. Phulia Para at Santipur block by retrofitting of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division- I, PHE Dte (Sl.no.12) | Assistant Engineer-I | Junior Engineer-II | ORD/000163/2023-2024 | 2121/NAD-I | 04/09/2023 | 25/09/2023 | CHOWDHURY & CO. | 12.91 | 12.86 | 99.66 | 100
15 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Conversion of IEP to AIRP at Goalpur Zone-I Water Supply Scheme under Shantipur Block of capacity 15 Cu.m/hr inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000237/2023-2024 | 2344/NAD-I | 03/10/2023 | 30/08/2026 | SATYABRATA CHAKRABORTY | 67.28 | 0 | 0 | 100
16 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Nabla, Goalpur Zone-I and Goalpur Zonr-II , Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla and Goalpur Water Supply S | SM/09972 | Augmentation | Construction of Back Wash Water Holding Tank and Land development and allied works at Head work site of Goalpur Zone-I PWSS under Shantipur Block under Nadia Arsenic Division- I P.H.E Dte | Assistant Engineer-I | Junior Engineer-II | ORD/000289/2023-2024 | 32/AE-I/NAD-I | 19/01/2024 | 11/09/2025 | SATYABRATA CHAKRABORTY | 4.82 | 0 | 0 | 100
Total | [13 empty] | 382.79 | 293.95 | 76.79