## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. | SM/10650 | Augmentation | Retrofitting work at Baranbria, Srirampur, Kalupur, Kani Bamni, Bagdia Mouza inconnection with Augmentation to accommodate FHTC under JJM for Duttaphulia Zone-II Ground water based PWSS (Phase-II) Block ¿ Ranaghat-II, Dist (sl.11) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000241/2022-2023 | 537 / NAD-I | 13/03/2023 | 03/04/2023 | M/S TARAK CHANDRA PAUL | 31.77 | 30.88 | 97.18 | 0
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. | SM/10650 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 3005/NAD-I | 04/11/2022 | 04/11/2022 | Resource Division | 38.85 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. | SM/10650 | Augmentation | FHTC under Jaldhara / Jalswapna for Duttaphulia Z-II Part -II at Ranaghat-II Block by augmentation of Ground water Based PWSS for Duttaphulia Z-II W/S scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl.no. 03) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000092/2022-2023 | 1939 /NAD-I | 12/10/2022 | 10/01/2023 | M/S TARAK CHANDRA PAUL | 557.43 | 553.79 | 99.35 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. | SM/10650 | Augmentation | Retrofitting work at Ramnagar and Duttaphulia at Hanskhali Block under Jal Jeevna Mission in connection with augmentation of Duttaphulia Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000186/2023-2024 | 2160/NAD-I | 11/09/2023 | 02/10/2023 | MESSRS FREEDOM CONSTRUCTION | 75.74 | 73.64 | 97.23 | 100
Total | [13 empty] | 703.79 | 658.31 | 93.54