## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. | SM/10651 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 3155/NAD_I | 25/11/2022 | 25/11/2022 | Resource Division | 57.42 | 0 | 0 | 0
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. | SM/10651 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Nrisinghapur Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM of Nrisinghapur Piped W/S Scheme (sl.15) | Assistant Engineer-I | Junior Engineer-II | ORD/000023/2023-2024 | 1159 /NAD-I | 28/04/2023 | 13/05/2023 | CHOWDHURY & CO. | 13.02 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. | SM/10651 | Augmentation | Collection of Household data through mobile app for FHTC Connection at Following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Nrisinghapur ii)Gobindapur Zone-I iii)Gobindapur Zone-II | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000005/2023-2024 | 167/AE-I/NAD-I | 12/04/2023 | 27/04/2023 | HORIZEN | 4.84 | 4.84 | 99.99 | 44
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. | SM/10651 | Augmentation | Road Restoration Work along PMGSY Road under Nrisinghapur Ground Water Supply Scheme at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000259/2023-2024 | 2595/NAD-I | 17/11/2023 | 17/12/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 48.14 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. | SM/10651 | Augmentation | Providing FHTC under Jaldhara/Jal Swapna for Nrisinghapur at Santipur Block by augmentation of Ground water Based PWSS for Nrisinghapur W/S Scheme under Nadia Arsenic Division -I ,P.H.E.Dte.(Sl.No.05) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000050/2022-2023 | 1689 / NAD-I | 08/09/2022 | 23/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 864.56 | 0 | 0 | 75
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Nrisinghapur Ground Water Based Piped Water Supply Scheme , Block-Santipur, District-Nadia. | SM/10651 | Augmentation | Reconnection at Beledanga, Uttarpara, Chandkuri, Harinadi, Sahebdanga laying of pipeline and rising main at Beledanga, Uttarpara, Chandkuri, Harinadi, Sahebdanga under Harinadi G.P. & supply of Sluice Valve with construction of chamber at H/W site and 2nd, 3rd, 4th Pump House under Jal Jeevan Mission (JJM) for Santipur Block by retrofitting of Ground Water Based PWSS for Nrisinghapur W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000017/2024-2025 | 1039/NAD-I | 08/07/2024 | 04/05/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 7.72 | 0 | 0 | 100
Total | [13 empty] | 995.7 | 4.84 | 0.49