## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Debagram Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. | SM/10654 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/JalSwapna for Debogram Phase-II at Ranaghat-II Block by augmentation of Ground Water based PWSS for Debogram Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000049/2022-2023 | 1688/NAD-I | 08/09/2022 | 07/12/2022 | UMWELT ENGINEER PVT. LTD. | 399.59 | 0 | 0 | 99
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Debagram Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. | SM/10654 | Augmentation | Providing FHTC and laying dedicated pipeline for Kamargaria & Debogram Village in connection with Debagram Water Supply Scheme within Nadia Arsenic Division-I, PHE Dte under Jal Jeevan Mission. (Sl. No. 04) |  |  | ORD/000027/2025-2026 | 157/NAD-I | 28/04/2025 | 27/06/2025 | M/S A.K. CONSTRUCTION | 82.68 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Debagram Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. | SM/10654 | Augmentation | Providing FHTC and laying dedicated pipeline for Sijdia, Dakhin Rameswarpur,Anatapur, Mithapur & aismali Village in connection with Debagram Water Supply Scheme under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000080/2025-2026 | 581/NAD-I | 10/07/2025 | 08/09/2025 | SUMAN CHAKRABORTY | 96.78 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by Augmentation under JJM for Debagram Ground Water Based Piped Water Supply Scheme (Phase-II) , Block-Ranaghat-II, District-Nadia. | SM/10654 | Augmentation | Laying of additional pipelines under JJM at Garapota W/S Scheme in connection with Debagram W/ Scheme under Ranaghat-II block within Hanskhali Block Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) |  |  | ORD/000306/2024-2025 | 229/AE-II/NAD-I | 12/11/2024 | 27/11/2024 | JAGADANADAPUR CO-OPT LABOUR CONTTRACT AND CONSTRUTION SOCITY LTD. | 4.85 | 0 | 0 | 0
Total | [13 empty] | 583.9 | 0 | 0