## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - II Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000226/2021-2022 | 71/AE-II/NAD-I | 24/02/2022 | 26/03/2022 | UMWELT ENGINEER PVT. LTD. | 4.8 | 4.8 | 100 | 100
2 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Route Survey for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - II Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000225/2021-2022 | 70/AE-II/NAD-I | 24/02/2022 | 26/03/2022 | UMWELT ENGINEER PVT. LTD. | 4.67 | 4.67 | 100 | 100
3 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Matikumra ii)Duttaphulia Zone-I iii)Duttaphulia Zone-II | Assistant Engineer-I ,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000004/2023-2024 | 166/AE-I/NAD-I | 12/04/2023 | 27/04/2023 | TECH VISION | 4.84 | 4.84 | 99.99 | 40
4 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Retrofitting work at Duttaphulia Mouza inconnection with Augmentation to accomodate FHTC under JJM for Duttaphulia Zone- II Ground water based piped watrer supply scheme ( Phase- I ) Block- Ranaghat -II Dist- Nadia under Nadia Arsenic Division-I , P.H.E Dte.(Sl.No. 08)" | Assistant Engineer-II | Junior Engineer-IV | ORD/000078/2023-2024 | 1384/NAD-I | 16/05/2023 | 15/06/2023 | MESSRS FREEDOM CONSTRUCTION | 72.08 | 71.49 | 99.19 | 100
5 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1781/NAD-I | 22/09/2022 | 22/09/2022 | Resource Division | 20.94 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Duttaphulia Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Duttaphulia Zone-II (Phase-I) under JJM (Sl.no.09) | Assistant Engineer-II | Junior Engineer-IV | ORD/000037/2023-2024 | 1362 / NAD-I | 12/05/2023 | 27/05/2023 | DULAL MAJUMDER | 13.03 | 12.95 | 99.34 | 100
7 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Surging of existing Tube Well situated at the 5th Tube Well site at Duttaphulia Zone-II Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000079/2024-2025 | 204/AE-II/NAD-I | 24/09/2024 | 01/10/2024 | M/S DIPAK ENTERPRISE | 0.64 | 0.64 | 100 | 100
8 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Surging of existing Tube Well situated at thr 2nd Tube Well site at Duttaphulia Zone-II Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000078/2024-2025 | 201/AE-II/NAD-I | 24/09/2024 | 01/10/2024 | BUDDHADEV MONDAL | 0.64 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Restoration of damages pipelines from Duttaphulia more to BSF camp in Ranaghat- II, Block under Nadia Arsenic Division-I,PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000004/2024-2025 | 142/AE-II/NAD-I | 07/06/2024 | 07/07/2024 | BUDDHADEV MONDAL | 4.19 | 4.19 | 99.91 | 100
10 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 68/NAD-I | 16/01/2024 | 16/01/2024 | Resource Division | 3.72 | 0 | 0 | 0
11 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-II (Part-I) at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water SUpply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000030/2022-2023 | 1463/NAD-I | 18/08/2022 | 06/10/2023 | APURBA MANDAL | 321.95 | 248.83 | 77.29 | 85
12 | NADIA |  | Eastern Mechanical | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III , IV and V (Zone-II) (Phase-I) under Duttapulia ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10659) | Assistant Engineer | Junior Engineer | ORD/000643/2024-2025 | 2680/EMD | 20/11/2024 | 30/06/2025 | S.S.ENTERPRISES | 50.99 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Balance work for revamping / upgradation of the hydraulic parameters at Muchiphulbari, Dhakuria & Baranberia Mouza in connection with Itaberia PWSS & Duttaphulia PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000033/2025-2026 | 167/NAD-I | 29/04/2025 | 27/10/2025 | MS MAA BHABANI ENTERPRISE | 95.54 | 0 | 0 | 0
14 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Providing FHTC and laying dedicated pipeline for Gangsara & Duttaphulia Village in connection Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme , Under Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. (Sl.05) | Assistant Engineer-II |  | ORD/000006/2025-2026 | 74/NAD-I | 16/04/2025 | 15/06/2025 | SHYAMAL SHIL | 94.18 | 0 | 0 | 0
15 | NADIA |  | Nadia Arsenic Division I | Augmentation to accommodate FHTC for Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme (Phase-I), Block-Ranaghat-II, District-Nadia. | SM/10659 | Augmentation | Construction of Boundary wall and pathway Head work site of Duttaphulia Zone- II and Dubli Zone- I water supply Scheme in Ranaghat-II Block in connection with Duttaphulia Zone-I W/S Scheme under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (sl.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000019/2025-2026 | 137/NAD-I | 23/04/2025 | 22/06/2025 | CFS MANAGEMENT PRIVATE LIMITED | 38.99 | 0 | 0 | 0
Total | [13 empty] | 731.2 | 352.41 | 48.2